## Master Schedule by Chapter
Schedule of Host Country Activities
ACTIVITY |  |  | DURATION | REMARKS
B | Host Country Role
| B.1 | Share eGreen-book with all HOC and PCOs stakeholders | Jan-2019 | -
| B.2 | Discuss logistical requirements with ADB | Jul-2021 | -
| B.3 | Provide logistical requirements in accordance with the Green Book | Jul-2021 to May-2022 | -
B | Host Country Organizing Committee and Organization Chart
| B.4 | Send ADB formal invitation | Nov-2018 | -
| B.5 | Governor takes over as Chair of Board of Governors | May-2021 | -
| B.6 | Inform ADB of appointment of Host Country Coordinator and project director | Jul-2021 | -
| B.7 | Provide composition of organizing committee and organization chart with detailed list of responsibilities | Jul-2021 | -
| B.8 | Establish channel of communication with ADB and working-level focal points | Jul-2021 | -
| B.9 | Provide ADB with table of focal persons | Sep-2021 | -
B | Host Country Role: Professional Congress Organizer
| B.10 | Hire a PCO to assist in organizing the Annual Meeting | Jan-2021 | -
| B.11 | Invite PCO to attend previous Annual Meeting | May-2021 | -
| B.12 | Invite PCO to participate in the ADB establishment mission | Jul-2021 | -
| B.13 | Determine communication channels among PCO, host country, and ADB | Jul-2021 | -
| B.14 | Provide ADB with PCO organizational chart and assignment of responsibilities | Jul-2021 | -
1 | Budget
| 1.1 | Review and agree on the cost- sharing agreement between ADB and /HC | Jan-2019 | -
| 1.2 | Sign the MOU, with related cost-sharing and eGreen-book | May-2020 | -
| 1.3 | HC draft budget for all elements of the event | Nov-2020 | -
| 1.4 | Identify events and services that may be of interest to sponsors and update expenditure | Jun-2021 | -
| 1.5 | Ensure all payments are settled and send pending bills to ADB | May-2022 | -
| 1.6 | Provide breakdown of costs incurred by host country and sponsors | Jun-2022 | -
2 | ADB Seminars
| 2.1 | Establish host country seminars focal point | Jul-2021 | -
| 2.2 | Provide feedback on draft seminar list | Sep-2021 | -
| 2.3 | Propose moderators and speakers from host country for ADB seminar series | Sep-2021 | -
| 2.4 | Discuss initial logistical requirements with ADB | Aug-2021 | -
| 2.5 | Confirm logistical arrangements for all seminars with ADB | Feb-2022 | -
| 2.6 | Discuss content and arrangements for live streaming of key official events as well as ADB videos and promotional materials of sponsors/partners on LCD screens | Feb-2022 | -
| 2.7 | Provide logistical requirements and local staff required for seminar series | May-2022 | -
2 | Business Session
| 2.8 | Confirm the Chair's availability to chair the Business Session (as per the co-chairing schedule proposed to the Organizing Committee) | Dec-2021 | -
| 2.9 | Determine date, time, and venue of ADB President's courtesy call on the Chair | Dec-2021 | -
| 2.1 | Confirm the schedule for the briefing of the Chair and Vice-Chairs by the Secretary | Dec-2021 | -
| 2.11 | Confirm if the Chair will deliver a combined statement (opening and country statements) or separate statements | Dec-2021 | -
| 2.12 | Discuss and confirm logistical arrangements for the business session (including a dry run before the business session) | Feb-2022 | -
2 | Governors’ Plenary
| 2.13 | Discuss logistical arrangements | Jul-2021 | -
| 2.14 | Confirm logistical arrangements (including dry run) | Feb-2022 | -
| 2.15 | Decide who will moderate the plenary (confirm Chair's availability if decided upon) | Mar-2022 | -
2 | Host Country Events
| 2.16 | Share and consult ADB on the program of events, including speakers and moderators | Aug-2021 | -
| 2.17 | Submit proposals for host country day seminars, if any | Oct-2021 | -
| 2.18 | Provide ADB with an executive summary of the program | Feb-2022 | -
| 2.19 | Provide ADB with a synopsis of the program for inclusion in the post-Annual Meeting publication, Highlights | May-2022 | -
2 | Networking Events Program
| 2.2 | Identify possible locations for ADB and host country networking events | Jul-2021 | -
| 2.21 | Discuss schedules and procedures for organizing networking events | Jul-2021 | -
| 2.22 | Advise ADB of proposals for Tours Program, if any | Jul-2021 | -
| 2.23 | Advise ADB of proposals for government-hosted official networking events, and arrange site visits | Jul-2021 | -
| 2.24 | Confirm list of official networking events | Nov-2021 | -
| 2.25 | Advise ADB of any Media tour programs or media tours being planned, if any | Nov-2021 | -
| 2.26 | Advise ADB of any Tours Program, and post information on website | Nov-2021 | -
| 2.27 | Provide list of names of host country special invitees (i.e., local VIPs) | Feb-2022 | -
| 2.28 | Provide list of names of incumbent members of diplomatic corps of ADB members in host country | Feb-2022 | -
| 2.29 | Provide detailed protocol scenarios and information on transport for VIPs at host country networking events | Feb-2022 | -
| 2.3 | Prepare invitations to host country events, where relevant, and send by email | Apr-2022 | -
| 2.31 | Implement Tours Program (if any) | May-2022 | -
2 | Opening Session Arrangements
| 2.32 | Discuss usual opening session protocol scenario | Jul-2021 | -
| 2.33 | Decide if there will be a cultural event and videos. Inform that ADB will show a corporate video before the opening session as delegates are coming in the session hall | Jul-2021 | -
| 2.34 | Inform that ADB President will use a speech prompter during the opening session, and will need to rehearse at the venue of the opening session before the event | Jul-2021 | -
| 2.35 | Discuss webcasting the opening session | Jul-2021 | -
| 2.36 | Confirm proposed seating plan. Inform that media will be given a designated seating area and a platform for photographers and broadcast media | Nov-2021 | -
| 2.37 | Advise ADB of Guest of Honor | Jan-2022 | -
| 2.38 | Provide list of members of diplomatic corps and local VIPs to be invited | Jan-2022 | -
| 2.39 | Advise ADB on webcasting of opening session | Jan-2022 | -
| 2.4 | Discuss opening session scenario; provide feedback to ADB | Jan-2022 to May-2022 | -
| 2.41 | Finalize arrangements for opening session in consultation with ADB | Apr-2022 | -
| 2.42 | Implement opening session protocol scenario | May-2022 | -
2 | Pre- and Post-Meeting Tours
| 2.43 | Coordinate production of information, if any | Jul-2021 to Sep-2021 | -
| 2.44 | Post brochure or information on tours and registration requirements on host country website | Nov-2021 | -
| 2.45 | Organize registration, payment, if any, and implementation of tours | Dec-2021 to May-2022 | -
2 | Sponsored Seminar Program
| 2.46 | Host country shortlists vendors (catering, stage/lighting, technical equipment, shipping) and identifies proposed space for sponsored seminars | Sep-2021 | -
| 2.47 | Sponsors coordinate directly with selected vendors on requirements | Jan-2022 | -
3 | Meetings and ADB Missions
| 3.1 | Arrange and host ADB initial assessment mission | Jun-2017 | -
| 3.2 | Arrange and host ADB strategic directions mission | Aug-2018 | -
| 3.3 | Send large observer team to previous/current Annual Meeting | May-2021 | -
| 3.4 | Identify the Missions required throughout pre-production and schedule with all involved | Jun-2021 | -
| 3.5 | Setup weekly progress meetings with ADB and Host Country Secretariat. | Jun-2021 | -
| 3.6 | Weekly or bi-monthly Progress meetings | Jul-2021 to May-2022 | -
| 3.7 | Host Country to establish Organizing Committee and any subcommittees | Jun-2021 | -
| 3.8 | Arrange and host ADB establishment mission | Jun-2021 | -
| 3.9 | Host Country to visit ADB | Nov-2021 | -
| 3.1 | Arrange and host ADB President's visit to host city | Nov-2021 | -
| 3.11 | Arrange and host ADB technical mission to host city | Feb-2022 | -
| 3.12 | Provide feedback to ADB on experience hosting Annual Meeting. PCO or Host Country to organize a Debrief meeting with all stakeholders involved | May-2022 | -
| 3.13 | PCO or Host Country to provide a final post event report | May-2022 | -
5 | Branding the Annual Meeting
| 5.1 | Host country begins to develop the Annual Meeting icon | Jul-2020 | -
| 5.2 | Selected design is shared with ADB for comments | Oct-2020 | -
| 5.3 | Host country participates in the Annual Meeting the year before they host through a Host country booth and a Host country event | May-2021 | -
| 5.4 | ADB develops the Logo Guidelines and updates Chapter 3 of the Green Book | Jun-2021 | -
| 5.5 | Technical mission to the venue and meeting of relevant suppliers | Feb-2022 | -
| 5.6 | Begin production of event materials | Mar-2022 | -
| 5.7 | Installation of event materials | Apr-2021 to May-2021 | -
6 | Hotel Accommodation
| 6.1 | Write to general managers to request room reservations for Annual Meeting participants | Dec-2020 | -
| 6.2 | Block book 1000 hotel rooms and suites for all official participants and ADB personnel | Dec-2020 | -
| 6.3 | Agree with ADB on agent (PCO) to handle hotel bookings | Jul-2021 | -
| 6.4 | Decide, in consultation with ADB, which hotels to use for which guest category, as well as hotel accommodation booking procedures, terms and conditions (e.g., cut-off time for reserving rooms and a no-show policy) | Jul-2021 | -
| 6.5 | Pilot test hotel booking procedure, in consultation with ADB | Sep-2021 | -
| 6.6 | Decide the procedure for handling tax exemption of ADB personnel paid through ADB master account | Oct-2021 | -
| 6.7 | Block book hotel accommodation for each country delegation | Oct-2021 | -
| 6.8 | Post information about hotel bookings on host country website | Nov-2021 | -
| 6.9 | Process hotel reservations, cancellations | Jan-2022 to May-2022 | -
| 6.1 | Provide reports on hotel bookings to ADB as required | Jan-2022 to May-2022 | -
7 | Space Requirements: Offices
| 7.1 | Ensure that sufficient offices with adequate soundproofing will be available | Jul-2021 | -
| 7.2 | In consultation with ADB, prepare plans and layouts (Floorplans) of ADB offices as required | Jul-2021 | -
| 7.3 | Allocate offices to appropriate function room within the occupancy schedule and share with all stakeholders | Aug-2021 | -
| 7.4 | Provide offices to advance team (i.e., Secretariat team, Registration team and Media team) | Apr-2022 | -
| 7.5 | Ensure ADB offices are furnished and equipped in accordance with ADB requirements | May-2022 | -
| 7.6 | Open all other ADB offices | May-2022 | -
7 | Space Requirements: Site Inspections and Space Allocations
| 7.7 | Agree on overall allocation of meeting and office rooms | Jul-2021 | -
| 7.8 | Submit proposed layouts and plans of ADB offices and meeting areas | Oct-2021 | -
| 7.9 | Agree with ADB on final space allocation and layouts | Nov-2021 | -
| 7.1 | Submit final floor plans for reproduction | Jan-2022 | -
| 7.11 | Agree on turnaround time for meeting and seminar rooms | Mar-2022 | -
| 7.12 | Agree on exact set-up and dismantling dates | Mar-2022 | -
| 7.13 | Appoint room managers to oversee each venue where meetings and events will take place | Mar-2022 | -
| 7.14 | Ensure that all meeting spaces are set up in accordance with requirements one hour before the meeting or event for checking | May-2022 | -
8 | Protocol
| 8.1 | Discuss Host Country protocol practices with ADB and propose a planning schedule | Jul-2021 | -
| 8.2 | Propose VIP arrangement and protocol | Jul-2021 | -
| 8.3 | Plan for Protocol Mission and propose subject discussion points | Nov-2021 | -
| 8.4 | Discuss Airport arrangements and courtesies, ground transport, courtesy calls, seating arrangements at key events and receptions | Nov-2021 | -
| 8.5 | If the Guest of Honor is the head of state or government of Host Country, arrange for ADB protocol team to meet their counterparts | Feb-2022 | -
9 | Visas, Immigration and Customs Clearance
| 9.1 | Inform ADB of procedures for facilitating issuance of visas including any special requirements for media and NGOs | Aug-2021 | -
| 9.2 | Confirm waiver of visa processing fees for ADB personnel | Aug-2021 | -
| 9.3 | Advise whether visas may be issued on arrival; if so, determine procedure | Aug-2021 | -
| 9.4 | Provide ADB with list of countries whose citizens require visa | Aug-2021 | -
| 9.5 | Provide ADB with list of countries that have no visa-issuing embassy or consulate | Aug-2021 | -
| 9.6 | Post information on visa applications on host country website | Nov-2021 | -
| 9.7 | Provide a focal point for visa inquiries and facilitation | Nov-2021 | -
| 9.8 | Relay ADB's request to issue appropriate visas to participants to the host country's diplomatic or visa-issuing missions | Jan-2022 | -
| 9.9 | Process visas of Annual Meeting participants, including international media, as quickly as possible | Feb-2022 to Apr-2022 | -
9 | Tax and Customs Duty Exemption
| 9.1 | Confirm ADB privileges and immunities | Jul-2021 | -
| 9.11 | Advise ADB of procedures for implementing tax and duty exemption for hotels, shipment, equipment, liquor, and equipment and accessories used by international media, etc | Oct-2021 | -
| 9.12 | Issue any documentation required for hotels, shipping agent, etc | Nov-2021 | -
| 9.13 | Ensure hotels and other relevant entities implement tax exemption procedures | Apr-2022 to May-2022 | -
10 | Insurance
| 10.1 | Host country to provide comprehensive general liability insurance to cover the venue(s), equipment and vehicles provided for the Annual Meeting. | Jan-2020 | -
| 10.2 | ADB to communicate to all participants to arrange for their own medical, travel, and personal insurance while attending the meeting. | Jan-2021 | -
| 10.3 | All third party suppliers to provide their general liability insurance or if not, are informed that the onus of responsibility for provision of liability insurance is on them. | Jan-2021 | -
11 | Information & Conference Technology: AV and Technical Requirements
| 11.1 | Host country or PCO appoint an audio and visual production supplier and brief in all requirements | May-2021 | -
| 11.2 | Ensure the audio and visual production supplier has the capability to provide all infrastructure across the project including simultaneous translation booths, media center needs, webcasting gear etc. If not, alternative partners should be appointed at this stage of project planning | May-2021
| 11.3 | Identify if additional internet/download speed needs to be added to the existing infrastructure of the selected venues | Jul-2021 | -
| 11.4 | Discuss all wiring, equipment and webcasting requirements with ADB Technical Director and ensure clear lines of communication are established between the appointed suppliers and the ADB Technical Director. | Jul-2021 | -
| 11.5 | Start planning for the Technical Mission held in January or February | Nov-2021 to Dec-2022 | -
| 11.6 | Test wiring and equipment required | Feb-2022 | -
| 11.7 | Provide all wiring, equipment needed and webcasting to meet the requirements set out in the eGreenBook | Apr-2022 | -
| 11.8 | Install all LCD screens and seminar equipment (2 days before use) | Apr-2022 | -
11 | Information & Conference Technology: Telecommunications
| 11.9 | Identify where wireless two way radios are required and how many across all locations and brief AV and Technical team as to the supply of these onsite | May-2021 | -
| 11.1 | Provide telephones that can call internally, boss-to-secretary, and externally (within the city) as well as some international direct dial lines | Apr-2022 | -
| 11.11 | Provide cell phones for ADB personnel for making local calls | Apr-2022 to May-2022 | -
| 11.12 | Share onsite communication plan (Communication Routing) to ADB and HC teams (refer to sample communication plan) | Apr-2022 | -
11 | Information & Conference Technology: Website
| 11.13 | Designate a focal point for the website who will liaise with ADB's web team | Oct-2020 | -
| 11.14 | Discuss design of website and procedure for posting information | Jan-2021 | -
| 11.15 | Launch Annual Meeting website (on the last day of the previous Annual Meeting) | May-2021 | -
| 11.16 | Link host country tourist websites to Annual Meeting website | Jun-2021 | -
| 11.17 | Provide photos of at least 300 dpi quality | Jul-2021 | -
| 11.18 | Provide comments on format and content of web page | Jul-2021 | -
| 11.19 | Post information on hotel bookings, car rentals, visa applications | Sep-201 | -
| 11.2 | Link formatted version on ADB website with relevant host country websites | Nov-2021 | -
| 11.21 | Submit mobile app to ADB for comments | Jan-2022 | -
| 11.22 | Launch mobile app | Feb-2022 | -
12 | Sponsorship, Partnership and Gifts
| 12.1 | Discuss with ADB sponsorship/partnership and promotional opportunities and agreed approval mechanism for sponsors and acknowledgement of sponsors | Aug-2021 | -
| 12.2 | Discuss strategy for attracting sponsors/partners | Aug-2021 | -
| 12.3 | Review and provide input into draft sponsors’ brochure | Aug-2021 | -
| 12.4 | Nominate sponsors for official events | Sep-2021 to Feb 2022 | -
| 12.5 | Coordinate promotional banners and other materials with ADB, in accordance with the Branding Guidelines | Sep-2021 to Feb 2022 | -
| 12.6 | Consult ADB on sponsorship and partnership proposals and sponsors' materials | Sep-2021 to Feb 2022 | -
| 12.7 | Agree on location of sponsors'/partners’ areas, signs | Feb-2022 | -
| 12.8 | Finalize all sponsorship/partnership matters in consultation with ADB | Mar-2022 | -
| 12.9 | Provide ADB with complete list of sponsors/partners and their promotion activities | Mar-2022 | -
| 12.1 | Identify what gifts/souvenirs are required across all areas of the Annual Meeting. VIP’s vs Participants | Jan-2022 | -
| 12.11 | Advise ADB on any souvenir items to be given to participants | Jan-2022 | -
13 | Accreditation and Invitations
| 13.1 | Provide feedback on list of observers to be invited, and suggest any additional observers to be invited for inclusion in the Board paper | Jul-2021 | -
| 13.2 | Agree with ADB procedure for issuing invitations | Jul-2021 | -
| 13.3 | Review lists of participants from previous Annual Meeting | Jul-2021 | -
| 13.4 | Draft invitation copy and eDM (Electronic direct mail) design/template and provide example to ADB | Nov-2021 | -
| 13.5 | Provide names and e-mail addresses of contact persons for host country guests, including local dignitaries, members of the diplomatic corps and members of host country secretariat, who will forward the ADB invitation to invited host country guests | Apr-2022 | -
| 13.6 | Provide final list of invitees for the host country luncheon to ADB at least 5 days before the event | May-2022 | -
| 13.7 | Send invitations (by email) for host country luncheon and host country reception to invitees in advance | May-2022 | -
14 | Airport Reception
| 14.1 | Discuss airport requirements | Jul-2021 | -
| 14.2 | Inspect airport | Jul-2021 | -
| 14.3 | Discuss visa upon arrival, if any, and customs requirements for delegates (e.g., international media) | Jul-2021 | -
| 14.4 | Identify signage and branding requirements throughout the airport and arrival/reception areas | Jul-2021 | -
| 14.5 | Provide draft airport reception plan | Feb-2022 | -
| 14.6 | Finalize VIP and other participants' reception procedures | Feb-2022 | -
| 14.7 | Provide airport floor plans (for inclusion in arrangements paper) | Feb-2022 | -
| 14.8 | Prepare staffing plan to share with the International Airport management team | Feb-2022 | -
| 14.9 | Train all staff and volunteers | Apr-2022 | -
| 14.1 | Conduct a dry run of reception procedures with the ADB advance party | Apr-2022 | -
| 14.11 | Set up reception desk, separate immigration lane, shuttle bus stop, and signs | May-2022 | -
15 | Security
| 15.1 | Appoint security focal point | Jul-2021 | -
| 15.2 | Discuss general security requirements with ADB | Jul-2021 | -
| 15.3 | Continue consultations with ADB Security Coordinator | Sep-2021 to May-2022 | -
| 15.4 | Provide plan of security perimeter, access and drop-off points, and traffic flow | Dec-2021 | -
| 15.5 | Prepare security guard schedule for all areas of the AM venues | Dec-2021
| 15.6 | Determine security measures and access for service vehicles, deliveries | Dec-2021 | -
| 15.7 | Present security plan, including emergency evacuation, to ADB head of security | Feb-2022 | -
| 15.8 | Discuss detailed security scenarios with ADB Security Coordinator | Feb-2022 | -
| 15.9 | Provide telephone numbers for emergency information | Apr-2022 | -
| 15.1 | Design color-coded badges for local staff and police access to restricted areas such as the Governors' Lounge | Apr-2022 | -
| 15.11 | Meet with ADB Security Advisory Committee every day during Annual Meeting | May-2022 | -
16 | Transport and Traffic Flow
| 16.1 | Discuss requirements for transport and traffic flow with ADB | Jul-2021 | -
| 16.2 | Determine access to venue as well as pick-up and drop-off points | Jul-2021 | -
| 16.3 | Determine how to allow access for (i) registration, and (ii) delivery of publications | Dec-2021 | -
| 16.4 | Determine parking areas for all vehicles including participants | Dec-2021
| 16.5 | Share Transport, parking and Traffic flow plan with all parties | Jan-2022
| 16.6 | Review arrangements for assigned cars and shuttle bus schedules | Feb-2022 | -
| 16.7 | Review arrangements for traffic flow at meeting venue and networking events venues | Feb-2022 | -
| 16.8 | Review transport advisory for participants | Feb-2022 | -
| 16.9 | Finalize parking, vehicle movement signage requirements for all areas of AM | Feb-2022
| 16.1 | Determine schedule and itineraries of shuttle buses | Mar-2022 | -
| 16.11 | Finalize shuttle bus schedule booklet, if any, in consultation with ADB | Apr-2022 | -
| 16.12 | Train all drivers on routes to and from all meeting venues | Apr-2022 to May-2022 | -
| 16.13 | Conduct dry run for shuttles with ADB advance team | Apr-2022 | -
17 | Registration
| 17.1 | Appoint a host country counterpart | Jul-2021 | -
| 17.2 | Determine access to registration center, considering security measures | Oct-2021 | -
| 17.3 | Provide comments on draft sample badges | Nov-2021 | -
| 17.4 | Agree with ADB on the use of forwarding facility to promote host country events (frequency of broadcast e-mails) | Nov-2021 | -
| 17.5 | Determine access procedure for nonregistered meeting invitees, if any | Feb-2022 | -
| 17.6 | Assign focal person to coordinate registration of members of Host Country Secretariat for their registration | Feb-2022 | -
| 17.7 | Determine how to register, provide access to local staff, and inform ADB | Feb-2022 | -
| 17.8 | Assign focal person to register host country dignitaries and special invitees | Feb-2022 | -
| 17.9 | Provide facilities and technical personnel to test and support ADB registration equipment | Feb-2022 | -
| 17.1 | Agree on and establish accreditation and registration procedures onsite | Feb-2022 | -
| 17.11 | If applicable, provide a prototype of locally engaged staff badges to security, police, and ADB | Apr-2022 | -
| 17.12 | Provide download instructions for the ADB App and provide a user guide to registration staff as part of the training. | Apr-2022 | -
| 17.13 | During the Annual Meeting, post ADB staff at the registration center to accredit onsite registrants | May-2022 | -
18 | Meeting Services
| 18.1 | PCO/HC to appoint a dedicated contact managing the meeting services throughout the Annual Meeting. | Oct-2021 | -
| 18.2 | PCO/HC to ensure adequate furniture and infrastructure is ordered to provide counters and services listed on the Meeting Services Checklist | Oct-2021 | -
| 18.3 | HC/PCO to allocate a suitable space for each meeting service requirements and add to scaled floorplans and Utilization table | Feb-2022 | -
| 18.4 | HC to allocate staff to each Meeting Service. Ensure these staff are properly briefed at each location | Mar-2022 | -
| 18.5 | Ensure all meeting services are finalised with ADB. Staffing, meeting service location and signage is agreed/approved | Mar-2022 | -
19 | Meeting Setups and Space Allocation
| 19.1 | Agree on overall allocation of meeting and office rooms | Jul-2021 | -
| 19.2 | Submit proposed layouts and plans of ADB offices and meeting areas | Oct-2021 | -
| 19.3 | Agree with ADB on final space allocation and layouts | Nov-2021 | -
| 19.4 | Submit final floor plans for reproduction | Jan-2022 | -
| 19.5 | Agree on turnaround time for meeting and seminar rooms | Mar-2022 | -
| 19.6 | Agree on exact set-up and dismantling dates | Mar-2022 | -
| 19.7 | Ensure all equipment, furniture and setup requirements is ordered for each meeting and event | Mar-2022 | -
| 19.8 | Appoint room managers to oversee each venue where meetings and events will take place | Mar-2022 | -
| 19.9 | Ensure that all meeting spaces are set up in accordance with requirements one hour before the meeting or event for checking | May-2022 | -
20 | Host Country Media Outreach Program
| 20.1 | Share host country’s outreach program with ADB | Aug-2021 | -
| 20.2 | Assist ADB with media and outreach program in host country, as needed | Aug-2021 | -
| 20.3 | Implement press related program in consultation with ADB | Jan-2022 to Apr-2022 | -
20 | Media and Communications
| 20.4 | Appoint a senior official as host country's Media and Communications focal point | Jul-2021 | -
| 20.5 | Discuss media and outreach activities for the period before and during the Annual Meeting. Inform that ADB President will hold a press conference during his pre-Annual Meeting visit | Aug-2021 | -
| 20.6 | Discuss extent of media coverage, including local, regional, and international print and broadcast media participation | Aug-2021 | -
| 20.7 | Discuss media partnerships and inform that ADB will partner with regional and international media organizations to raise awareness of the Annual Meeting, the host country could consider partnership with local media organizations | Aug-2021 | -
| 20.8 | Discuss accreditation and facilitation of visa applications and related travel requirements for international media | Aug-2021 | -
| 20.9 | Discuss customs clearance of audiovisual and photography equipment and other formalities for international media | Aug-2021 | -
| 20.1 | Provide list of journalists based in the host country, including their email addresses, for the online invitation | Dec-2021 | -
| 20.11 | Assist local media to register online | Jan-2022 | -
20 | Multimedia and Social Media
| 20.12 | Inform that ADB will use multimedia products such as still photos, video news releases, and podcasts to be uploaded on ADB.org for promotion of Annual Meeting | Jul-2021 | -
| 20.13 | Inform that ADB will use social media such as Facebook and Twitter to disseminate information through ADB’s institutional platforms and Annual Meeting apps | Jul-2021 | -
21 | Catering and Refreshments
| 21.1 | Recommend three caterers that could provide refreshments for events and onsite food outlets. One of these caterers could be ‘inhouse’ or those already within the venue. | Jul-2021 | -
| 21.2 | Waive any fee imposed by convention center or meeting venues onon outside caterers | Jul-2021 | -
| 21.3 | Host Country to appoint a focal person to manage catering requirements across all areas of the Annual Meeting | Jul-2021
| 21.4 | Arrange for ADB to meet caterers to discuss requirements | Jul-2021 | -
| 21.5 | Ensure adequate kitchen and other facilities for the caterers | Jul-2021 | -
| 21.6 | HC to start completing a Master Catering schedule which includes all the catering requirements across all areas to share with ADB and Caterers/Venues. | Nov-2021
| 21.7 | Caterers to send menu selection to ADB for transmittal to event organizers | Dec-2021 | -
| 21.8 | Caterers to confirm with ADB that requirements will be met and of high standard | Mar-2022 | -
| 21.9 | Caterer to deliver goods and services and submit bill for payment | Apr-2022 to May-2022 | -
22 | Staff Support: Briefings
| 22.1 | Confirm date of hiring, training and briefing of locally engaged staff | Feb-2022 | -
| 22.2 | Set up appointment, venue, and equipment required for briefing by ADB | Apr-2022 | -
| 22.3 | Appoint locally engaged staff protocol and onsite briefing | May-2022 | -
22 | Staff Support: Locally Engaged Staff
| 22.4 | Discuss local staff requirements, sources | Jul-2021 | -
| 22.5 | Recommend three professional personnel agencies to source its local staff | Jul-2021 | -
| 22.6 | Host Country to propose engagement plan for for local staff | Jul-2021
| 22.7 | Advise ADB on relevant labor laws, appropriate remuneration, and terms and conditions | Jul-2021 | -
| 22.8 | Discuss with ADB arrangements for food, transport, and uniforms for local staff | Jul-2021 | -
| 22.9 | Advise ADB on source and recruitment of host country local staff | Nov-2021 | -
| 22.1 | If considered necessary, send a representative for the panel interviews of ADB local staff | Mar-2022 | -
| 22.11 | Train local staff in their jobs, including drivers of shuttle buses and liaison officers | Apr-2022 to May-2022 | -
| 22.12 | Arrange briefings for local staff by host country and ADB Secretariat | Apr-2022 | -
22 | Staff Support: Liaison Officers
| 22.13 | Decide on provision of liaison officers | Jul-2021 | -
| 22.14 | Brief ADB on proposed use, procedures, training, and terms of reference of liaison officers | Oct-2021 | -
| 22.15 | Arrange briefing for liaison officers to be conducted with ADB | Apr-2022 | -
| 22.16 | Agree with ADB on assignment of liaison officers for key officials, including ADB President and spouse or partner | Apr-2022 | -
| 22.17 | Give ADB list of liaison officers and their cell phone numbers | Apr-2022 | -
| 22.18 | Set up meetings between liaison officers and their VIPs | May-2022 | -
23 | Furniture and Supplies
| 23.1 | Discuss with ADB all furniture, equipment, and supplies required | Jul-2021 | -
| 23.2 | HC or PCO to request inventory list from venues and start a Furniture Matrix which becomes the working document for HC, ADB and venues | Jul-2021 | -
| 23.3 | Share with ADB the furniture ordered or acquired for all business meetings | Jul-2021 | -
| 23.4 | Provide rental rates of equipment and services for seminars | Jul-2021 | -
| 23.5 | Provide photos of sample furniture, and set up equipment for ADB to check | Oct-2021 | -
| 23.6 | Procure any furniture and equipment required | Oct-2021 to Dec-2021 | -
| 23.7 | Ensure that the audio, video and other equipment and furniture provided are of appropriate ADB standards | Feb-2022 | -
24 | Procurement
| 24.1 | ADB and host country to meet with possible suppliers to discuss requirements, including sustainability requirements | Aug-2021 | -
| 24.2 | ADB and host country to start their procurement process | Sep-2021 | -
| 24.3 | Host country / ADB to finalize selection of their respective suppliers | Dec-2021 | -
| 24.4 | ADB and host country to send detailed information to suppliers | Jan-2022 | -
| 24.5 | ADB and host country to meet with suppliers to discuss issues, details, test and select items as necessary | Feb-2022 | -
| 24.6 | Host country / ADB to finalize arrangements for suppliers and providers | Apr-2022 | -
| 24.7 | Host country / ADB to check that all services and products are provided as required | May-2022 | -
25 | Sustainability Considerations
| 25.1 | Share Event Sustainability Management System Policy and ISO 20121 requirements with HOC team | Aug-2021 | -
| 25.2 | Review ADB's generic supplier contract with Sustainability Management Certificate; consider adopting it | Sep-2021 | -
| 25.3 | Propose waste management and conservation measures that can be put in place for the Annual Meeting | Sep-2021 | -
| 25.4 | Discuss sustainability considerations with supply chain | Sep-2021 to Oct-2021 | -
| 25.5 | Attend training at ADB HQ on sustainable events | Nov-2021 | -
| 25.6 | Confirm sustainability risk assessment for the Annual Meeting | Nov-2021 | -
| 25.7 | Set sustainability objectives and indicators; discuss these with supply chain | Dec-2021 | -
| 25.8 | Propose specific sustainable event activities for environmental, economic and social impacts at the Annual Meeting | Jan-2022 | -
| 25.9 | Coordinate with venue(s) and suppliers to monitor and measure sustainability results | Jan-2022 to May-2022 | -
| 25.1 | Communicate sustainability activities to HOC, local community and other stakeholders | Apr-2022 to May-2022 | -
| 25.11 | Provide previously-agreed, relevant data to measure implementation of sustainability objectives | May-2022 | -
26 | Printing Requirements for the Board of Directors
| 26.1 | Provide comments on Board Paper on Place and Date of Annual Meeting | Jan-2019 | -
| 26.2 | Provide comments on arrangements document | Aug-2021 | -
| 26.3 | Provide comments on Observers Paper | Sep-2021 | -
| 26.4 | Provide comments on CSO Invitees Paper | Sep-2021 | -
| 26.5 | Provide comments on hotel accommodation memo | Sep-2021 | -
| 26.6 | Provide comments on information bulletins (airport reception, liaison officers, airport arrangements, transport, communications and equipment, international telephone calls, return shipment, and badges) | Jan-2022 | -
| 26.7 | Provide comments on official events paper | Mar-2022 | -
26 | Printing: InfoMap and Digital Program of Events
| 26.8 | Provide input on InfoMap and digital Program of Events | Jan-2022 | -
| 26.9 | Provide telephone and cell phone numbers for directory | Feb-2022 | -
| 26.1 | Review final InfoMap and digital Program of Events | Feb-2022 | -
26 | Printing
| 26.11 | Use logo in promotional materials and on website | Mar-2021 to May-2022 | -
| 26.12 | Provide ADB with contact details of three printers to print documents onsite for ADB | Jul-2021 | -
| 26.13 | Print materials | Apr-2022 | -
27 | Payments by ADB
| 27.1 | ADB sends the supplier an invitation to register in supplier information Management system | Jul-2021 to Feb-2022 | -
| 27.2 | Suppliers complete the online supplier registration. | Jul-2021 to Feb-2022 | -
| 27.3 | ADB confirms the online registration. | after completing all the documentary requirements | -
| 27.4 | Suppliers send proposal, draft contract or agreement to ADB; negotiation commences | As required | -
| 27.5 | Advance payment process | After confirmation of online supplier registration | -
| 27.6 | For payments to be made after the Annual Meeting, ADB reviews the advance copy of bill using the catering and refreshments schedule or accommodation booking advice as a basis. | May-2022 | -
| 27.7 | Supplier prepares final bill in the agreed currency | May-2022 | -
| 27.8 | ADB brings original invoice or bill and supporting documents to ADB headquarters for processing. | May-2022 | -
| 27.9 | Processing of payment takes 2–3 weeks, assuming all documents are complete and the supplier information form and bank details are set up. | Mid-May to July 2022 | -
| 27.1 | Payment is through wire transfer and may take a maximum of 15 days after the value date for ADB’s bank to remit payment to the recipient bank of the supplier. | June to July 2022 | -
28 | Shipment
| 28.1 | Discuss shipment requirements with ADB | Jul-2021 | -
| 28.2 | Appoint focal person for shipment | Sep-2021 | -
| 28.3 | Inform ADB of appointed broker to handle shipments | Nov-2021 | -
| 28.4 | Submit necessary documents for tax exemption to shipping company | Jan-2022 | -
| 28.5 | Handle customs clearance and actual shipment from ADB | Mar-2022 to Apr-2022 | -
| 28.6 | Provide storage as necessary for ADB shipments | Apr-2022 | -
| 28.7 | Handle return shipments including packing, storage, and transport to port of exit | May-2022 | -

## Master Schedule by date
Schedule of Host Country Activities
CHAPTER | ITEM NO | CATEGORY | ACTIVITY | DURATION | REMARKS
3 | 3.1 | Meetings and ADB Missions | Arrange and host ADB initial assessment mission | 2016-06-01 | -
3 | 3.2 | Meetings and ADB Missions | Arrange and host ADB strategic directions mission | 2016-08-01 | -
B | B.4 | Host Country Role | Send ADB formal invitation | 2016-11-01 | -
B | B.1 | Host Country Role | Share eGreen-book with all HOC and PCOs stakeholders | 2017-01-01 | -
1 | 1.1 | Budget | Review and agree on the cost- sharing agreement between ADB and /HC | 2017-01-01 | -
26 | 26.1 | Printing Reqirements for the Board of Directors | Provide comments on Board Paper on Place and Date of Annual Meeting | 2017-01-01 | -
1 | 1.2 | Budget | Sign the MOU, with related cost-sharing and eGreen-book | 2018-05-01 | -
10 | 10.1 | Insurance | Host country to provide comprehensive general liability insurance to cover the venue(s), equipment and vehicles provided for the Annual Meeting. | 2018-06-01 | -
5 | 5.1 | Branding the Annual Meeting | Host country begins to develop the Annual Meeting icon | 2018-07-01 | -
5 | 5.2 | Branding the Annual Meeting | Selected design is shared with ADB for comments | 2018-10-01 | -
11 | 11.13 | Information & Conference Technology | Designate a focal point for the website who will liaise with ADB's web team | 2018-10-01 | -
1 | 1.3 | Budget | HC draft budget for all elements of the event | 2018-11-01 | -
6 | 6.1 | Hotel Accommodation | Write to general managers to request room reservations for Annual Meeting participants | 2018-12-01 | -
6 | 6.2 | Hotel Accommodation | Block book 1000 hotel rooms and suites for all official participants and ADB personnel | 2018-12-01 | -
B | B.10 | Host Country Role: | Hire a PCO to assist in organizing the Annual Meeting | 2019-01-01 | -
10 | 10.2 | Insurance | ADB to communicate to all participants to arrange for their own medical, travel, and personal insurance while attending the meeting. | 2019-01-01 | -
10 | 10.3 | Insurance | All third party suppliers to provide their general liability insurance or if not, are informed that the onus of responsibility for provision of liability insurance is on them. | 2019-01-01 | -
11 | 11.14 | Information & Conference Technology | Discuss design of website and procedure for posting information | 2019-01-01 | -
26 | 26.11 | Printing | Use logo in promotional materials and on website | Mar-2019 to May-2020 | -
B | B.5 | Host Country Role | Governor takes over as Chair of Board of Governors | 2019-05-01 | -
B | B.11 | Host Country Role: | Invite PCO to attend previous Annual Meeting | 2019-05-01 | -
3 | 3.3 | Meetings and ADB Missions | Send large observer team to previous/current annual meeting | 2019-05-01 | -
5 | 5.3 | Branding the Annual Meeting | Host country participates in the Annual Meeting the year before they host through a Host country booth and a Host country event | 2019-05-01 | -
11 | 11.1 | Information & Conference Technology | Host country or PCO appoint an audio and visual supplier and brief in all requirements | 2019-05-01 | -
11 | 11.2 | Information & Conference Technology | Ensure the audio and visual supplier has the capability to provide all infrastructure across the project including simultaneous translation booths, media center needs, webcasting gear etc. If not, alternative partners should be appointed at this stage of project planning | 2019-05-01
11 | 11.9 | Information & Conference Technology | Identify where wireless two way radios are required and how many across all locations and brief AV and Technical team as to the supply of these onsite | 2019-05-01 | -
11 | 11.15 | Information & Conference Technology | Launch Annual Meeting website (on the last day of the previous Annual Meeting) | 2019-05-01 | -
1 | 1.4 | Budget | Identify events and services that may be of interest to sponsors and update expenditure | 2019-06-01 | -
3 | 3.4 | Meetings and ADB Missions | Identify the Missions required throughout pre-production and schedule with all involved | 2019-06-01 | -
3 | 3.5 | Meetings and ADB Missions | Setup weekly progress meetings with ADB and HC Secretariat. | 2019-06-01 | -
5 | 5.4 | Branding the Annual Meeting | ADB develops the Logo Guidelines and updates Chapter 3 of the Green Book | 2019-06-01 | -
11 | 11.16 | Information & Conference Technology | Link host country tourist websites to Annual Meeting website | 2019-06-01 | -
B | B.2 | Host Country Role | Discuss logistical requirements with ADB | 2019-07-01 | -
B | B.6 | Host Country Role | Inform ADB of appointment of Host Country Coordinator and project director | 2019-07-01 | -
B | B.7 | Host Country Role | Provide composition of organizing committee and organization chart with detailed list of responsibilities | 2019-07-01 | -
B | B.8 | Host Country Role | Establish channel of communication with ADB and working-level focal points | 2019-07-01 | -
B | B.12 | Host Country Role: | Invite PCO to participate in the ADB establishment mission | 2019-07-01 | -
B | B.13 | Host Country Role: | Determine communication channels among PCO, host country, and ADB | 2019-07-01 | -
B | B.14 | Host Country Role: | Provide ADB with PCO organizational chart and assignment of responsibilities | 2019-07-01 | -
2 | 2.1 | Events: ADB Seminars | Establish host country seminars focal point | 2019-07-01 | -
2 | 2.15 | Events: Governors’ Plenary | Discuss logistical arrangements | 2019-07-01 | -
2 | 2.22 | Events: Networking Events Program | Identify possible locations for ADB and host country networking events | 2019-07-01 | -
2 | 2.23 | Events: Networking Events Program | Discuss schedules and procedures for organizing networking events | 2019-07-01 | -
2 | 2.24 | Events: Networking Events Program | Advise ADB of proposals for Tours Program, if any | 2019-07-01 | -
2 | 2.25 | Events: Networking Events Program | Advise ADB of proposals for government-hosted official networking events, and arrange site visits | 2019-07-01 | -
2 | 2.34 | Events: Opening Session Arrangements | Discuss usual opening session protocol scenario | 2019-07-01 | -
2 | 2.35 | Events: Opening Session Arrangements | Decide if there will be a cultural event and videos. Inform that ADB will show a corporate video before the opening session as delegates are coming in the session hall | 2019-07-01 | -
2 | 2.36 | Events: Opening Session Arrangements | Inform that ADB President will use a speech prompter during the opening session, and will need to rehearse at the venue of the opening session before the event | 2019-07-01 | -
2 | 2.37 | Events: Opening Session Arrangements | Discuss webcasting the opening session | 2019-07-01 | -
3 | 3.6 | Meetings and ADB Missions | Weekly or Fortnightly Progress meetings | Jul-2019 to May-2020 | -
3 | 3.7 | Meetings and ADB Missions | HC to establish Organizing Committee and any subcommittees | 2019-07-01 | -
3 | 3.8 | Meetings and ADB Missions | Arrange and host ADB establishment mission | 2019-07-01 | -
6 | 6.3 | Hotel Accommodation | Agree with ADB on agent (PCO) to handle hotel bookings | 2019-07-01 | -
6 | 6.4 | Hotel Accommodation | Decide, in consultation with ADB, which hotels to use for which guest category, as well as hotel accommodation booking procedures, terms and conditions (e.g., cut-off time for reserving rooms and a no-show policy) | 2019-07-01 | -
7 | 7.1 | Space Requirements: Offices | Ensure that sufficient offices with adequate soundproofing will be available | 2019-07-01 | -
7 | 7.2 | Space Requirements: Offices | In consultation with ADB, prepare plans and layouts (Floorplans) of ADB offices as required | 2019-07-01 | -
7 | 7.7 | Space Requirements: Site Inspections & Space Allocations | Agree on overall allocation of meeting and office rooms | 2019-07-01 | -
8 | 8.1 | Protocol | Discuss Host Country protocol practices with ADB and propose a planning schedule | 2019-07-01 | -
8 | 8.2 | Protocol | Propose VIP arrangement and protocol | 2019-07-01 | -
9 | 9.1 | Visa: Tax and Customs Duty Exemption | Confirm ADB privileges and immunities | 2019-07-01 | -
11 | 11.3 | Information & Conference Technology | Identify if additional internet/download speed needs to be added to the existing infrastructure of the selected venues | 2019-07-01 | -
11 | 11.4 | Information & Conference Technology | Discuss all wiring, equipment and webcasting requirements with ADB Technical Director and ensure clear lines of communication are established between the appointed suppliers and the ADB Technical Director | 2019-07-01 | -
11 | 11.17 | Information & Conference Technology | Provide photos of at least 300 dpi quality | 2019-07-01 | -
11 | 11.18 | Information & Conference Technology | Provide comments on format and content of web page | 2019-07-01 | -
13 | 13.1 | Accreditation and Invitations | Provide feedback on list of observers to be invited, and suggest any additional observers to be invited for inclusion in the Board paper | 2019-07-01 | -
13 | 13.2 | Accreditation and Invitations | Agree with ADB procedure for issuing invitations | 2019-07-01 | -
13 | 13.3 | Accreditation and Invitations | Review lists of participants from previous Annual Meeting | 2019-07-01 | -
14 | 14.1 | Airport Reception | Discuss airport requirements | 2019-07-01 | -
14 | 14.2 | Airport Reception | Inspect airport | 2019-07-01 | -
14 | 14.3 | Airport Reception | Discuss visa upon arrival, if any, and customs requirements for delegates (e.g., international media) | 2019-07-01 | -
14 | 14.4 | Airport Reception | Identify signage and branding requirements throughout the airport and arrival/reception areas | 2019-07-01 | -
15 | 15.1 | Security | Appoint security focal point | 2019-07-01 | -
15 | 15.2 | Security | Discuss general security requirements with ADB | 2019-07-01 | -
16 | 16.1 | Transport and Traffic Flow | Discuss requirements for transport and traffic flow with ADB | 2019-07-01 | -
16 | 16.2 | Transport and Traffic Flow | Determine access to venue as well as pick-up and drop-off points | 2019-07-01 | -
17 | 17.1 | Registration | Appoint a host country counterpart | 2019-07-01 | -
19 | 19.1 | Meeting Setups | Agree on overall allocation of meeting and office rooms | 2019-07-01 | -
20 | 20.4 | Media and Communications | Appoint a senior official as host country's Media and Communications focal point | 2019-07-01 | -
20 | 20.12 | Media and Communications | Inform that ADB will use multimedia products such as still photos, video news releases, and podcasts to be uploaded on ADB.org for promotion of Annual Meeting | 2019-07-01 | -
20 | 20.13 | Media and Communications | Inform that ADB will use social media such as Facebook and Twitter to disseminate information through ADB’s institutional platforms and Annual Meeting apps | 2019-07-01 | -
21 | 21.1 | Catering and Refreshments | Recommend three caterers that could provide refreshments for events and onsite food outlets. One of these caterers could be ‘inhouse’ or those already within the venue. | 2019-07-01 | -
21 | 21.2 | Catering and Refreshments | Waive any fee imposed by convention center or meeting venues onon outside caterers | 2019-07-01 | -
21 | 21.3 | Catering and Refreshments | Host Country to appoint a focal person to manage catering requirements across all areas of the Annual Meeting | 2019-07-01
21 | 21.4 | Catering and Refreshments | Arrange for ADB to meet caterers to discuss requirements | 2019-07-01 | -
21 | 21.5 | Catering and Refreshments | Ensure adequate kitchen and other facilities for the caterers | 2019-07-01 | -
22 | 22.4 | Staff Support: Locally Engaged Staff | Discuss local staff requirements, sources | 2019-07-01 | -
22 | 22.5 | Staff Support: Locally Engaged Staff | Recommend three professional personnel agencies to source its local staff | 2019-07-01 | -
22 | 22.6 | Staff Support: Locally Engaged Staff | Host Country to propose engagement plan for for local staff | 2019-07-01
22 | 22.7 | Staff Support: Locally Engaged Staff | Advise ADB on relevant labor laws, appropriate remuneration, and terms and conditions | 2019-07-01 | -
22 | 22.8 | Staff Support: Locally Engaged Staff | Discuss with ADB arrangements for food, transport, and uniforms for local staff | 2019-07-01 | -
22 | 22.13 | Staff Support: Liaison Officers | Decide on provision of liaison officers | 2019-07-01 | -
23 | 23.1 | Furniture and Supplies | Discuss with ADB all furniture, equipment, and supplies required | 2019-07-01 | -
23 | 23.2 | Furniture and Supplies | HC or PCO to request inventory list from venues and start a Furniture Matrix which becomes the working document for HC, ADB and venues | 2019-07-01 | -
23 | 23.3 | Furniture and Supplies | Share with ADB the furniture ordered or acquired for all business meetings | 2019-07-01 | -
23 | 23.4 | Furniture and Supplies | Provide rental rates of equipment and services for seminars | 2019-07-01 | -
26 | 26.12 | Printing | Provide ADB with contact details of three printers to print documents onsite for ADB | 2019-07-01 | -
28 | 28.1 | Shipment | Discuss shipment requirements with ADB | 2019-07-01 | -
27 | 27.1 | Payments by ADB | ADB sends the supplier information form to suppliers | Jul-2019 to Feb-2020 | -
27 | 27.2 | Payments by ADB | Suppliers complete the online supplier registration. | Jul-2019 to Feb-2020 | -
B | B.3 | Host Country Role | Provide logistical requirements in accordance with the Green Book | Jul-2019 to May-2020 | -
2 | 2.45 | Events: Pre- and Post-Meeting Tours | Coordinate production of information, if any | Jul-2019 to Sep-2019 | -
2 | 2.4 | Events: ADB Seminars | Discuss initial logistical requirements with ADB | 2019-08-01 | -
2 | 2.18 | Events: Host Country Events | Share and consult ADB on the program of events, including speakers and moderators | 2019-08-01 | -
7 | 7.3 | Space Requirements: Offices | Allocate offices to appropriate function room within the occupancy schedule and share with all stakeholders | 2019-08-01 | -
9 | 9.1 | Visas | Inform ADB of procedures for facilitating issuance of visas including any special requirements for media and NGOs | 2019-08-01 | -
9 | 9.2 | Visas | Confirm waiver of visa processing fees for ADB personnel | 2019-08-01 | -
9 | 9.3 | Visas | Advise whether visas may be issued on arrival; if so, determine procedure | 2019-08-01 | -
9 | 9.4 | Visas | Provide ADB with list of countries whose citizens require visa | 2019-08-01 | -
9 | 9.5 | Visas | Provide ADB with list of countries that have no visa-issuing embassy or consulate | 2019-08-01 | -
12 | 12.1 | Sponsorship, Partnership and Gifts | Discuss with ADB sponsorship/partnership and promotional opportunities and agreed approval mechanism for sponsors and acknowledgement of sponsors | 2019-08-01 | -
12 | 12.2 | Sponsorship, Partnership and Gifts | Discuss strategy for attracting sponsors/partners | 2019-08-01 | -
12 | 12.3 | Sponsorship, Partnership and Gifts | Review and provide input into draft sponsors’ brochure | 2019-08-01 | -
20 | 20.1 | Host Country Media Outreach Program | Share host country’s outreach program with ADB | 2019-08-01 | -
20 | 20.2 | Host Country Media Outreach Program | Assist ADB with media and outreach program in host country, as needed | 2019-08-01 | -
20 | 20.5 | Media and Communications | Discuss media and outreach activities for the period before and during the Annual Meeting. Inform that ADB President will hold a press conference during his pre-Annual Meeting visit | 2019-08-01 | -
20 | 20.6 | Media and Communications | Discuss extent of media coverage, including local, regional, and international print and broadcast media participation | 2019-08-01 | -
20 | 20.7 | Media and Communications | Discuss media partnerships and inform that ADB will partner with regional and international media organizations to raise awareness of the Annual Meeting, the host country could consider partnership with local media organizations | 2019-08-01 | -
20 | 20.8 | Media and Communications | Discuss accreditation and facilitation of visa applications and related travel requirements for international media | 2019-08-01 | -
20 | 20.9 | Media and Communications | Discuss customs clearance of audiovisual and photography equipment and other formalities for international media | 2019-08-01 | -
24 | 24.1 | Procurement | ADB and host country to meet with possible suppliers to discuss requirements, including sustainability requirements | 2019-08-01 | -
25 | 25.1 | Sustainability Considerations | Share Event Sustainability Management System Policy and ISO 20121 requirements with HOC team | 2019-08-01 | -
26 | 26.2 | Printing Reqirements for the Board of Directors | Provide comments on arrangements document | 2019-08-01 | -
B | B.9 | Host Country Role | Provide ADB with table of focal persons | 2019-09-01 | -
2 | 2.2 | Events: ADB Seminars | Provide feedback on draft seminar list | 2019-09-01 | -
2 | 2.3 | Events: ADB Seminars | Propose moderators and speakers from host country for ADB seminar series | 2019-09-01 | -
2 | 2.48 | Events: Sponsored Seminar Program | Host country shortlists vendors (catering, stage/lighting, technical equipment, shipping) and identifies proposed space for sponsored seminars | 2019-09-01 | -
6 | 6.5 | Hotel Accommodation | Pilot test hotel booking procedure, in consultation with ADB | 2019-09-01 | -
11 | 11.19 | Information & Conference Technology | Post information on hotel bookings, car rentals, visa applications | 2019-09-01 | -
24 | 24.2 | Procurement | ADB and host country to start their procurement process | 2019-09-01 | -
25 | 25.2 | Sustainability Considerations | Review ADB's generic supplier contract with Sustainability Management Certificate; consider adopting it | 2019-09-01 | -
25 | 25.3 | Sustainability Considerations | Propose waste management and conservation measures that can be put in place for the Annual Meeting | 2019-09-01 | -
26 | 26.3 | Printing Reqirements for the Board of Directors | Provide comments on Observers Paper | 2019-09-01 | -
26 | 26.4 | Printing Reqirements for the Board of Directors | Provide comments on CSO Invitees Paper | 2019-09-01 | -
26 | 26.5 | Printing Reqirements for the Board of Directors | Provide comments on hotel accommodation memo | 2019-09-01 | -
28 | 28.2 | Shipment | Appoint focal person for shipment | 2019-09-01 | -
12 | 12.4 | Sponsorship, Partnership and Gifts | Nominate sponsors for official events | Sep-2019 to Feb 2020 | -
12 | 12.5 | Sponsorship, Partnership and Gifts | Coordinate promotional banners and other materials with ADB, in accordance with the Branding Guidelines | Sep-2019 to Feb 2020 | -
12 | 12.6 | Sponsorship, Partnership and Gifts | Consult ADB on sponsorship and partnership proposals and sponsors' materials | Sep-2019 to Feb 2020 | -
15 | 15.3 | Security | Continue consultations with ADB Security Coordinator | Sep-2019 to May-2020 | -
25 | 25.4 | Sustainability Considerations | Discuss sustainability considerations with supply chain | Sep-2019 to Oct-2019 | -
2 | 2.19 | Events: Host Country Events | Submit proposals for host country day seminars, if any | 2019-10-01 | -
6 | 6.6 | Hotel Accommodation | Decide the procedure for handling tax exemption of ADB personnel paid through ADB master account | 2019-10-01 | -
6 | 6.7 | Hotel Accommodation | Block book hotel accommodation for each country delegation | 2019-10-01 | -
7 | 7.8 | Space Requirements: Site Inspections & Space Allocations | Submit proposed layouts and plans of ADB offices and meeting areas | 2019-10-01 | -
9 | 9.11 | Visa: Tax and Customs Duty Exemption | Advise ADB of procedures for implementing tax and duty exemption for hotels, shipment, equipment, liquor, and equipment and accessories used by international media, etc | 2019-10-01 | -
17 | 17.2 | Registration | Determine access to registration center, considering security measures | 2019-10-01 | -
18 | 18.1 | Meeting Services | PCO/HC to appoint a dedicated contact managing the meeting services throughout the Annual Meeting. | 2019-10-01 | -
18 | 18.2 | Meeting Services | PCO/HC to ensure adequate furniture and infrastructure is ordered to provide counters and services listed on the Meeting Services Checklist | 2019-10-01 | -
19 | 19.2 | Meeting Setups | Submit proposed layouts and plans of ADB offices and meeting areas | 2019-10-01 | -
22 | 22.14 | Staff Support: Liaison Officers | Brief ADB on proposed use, procedures, training, and terms of reference of liaison officers | 2019-10-01 | -
23 | 23.5 | Furniture and Supplies | Provide photos of sample furniture, and set up equipment for ADB to check | 2019-10-01 | -
23 | 23.6 | Furniture and Supplies | Procure any furniture and equipment required | Oct-2019 to Dec-2019 | -
2 | 2.26 | Events: Networking Events Program | Confirm list of official networking events | 2019-11-01 | -
2 | 2.27 | Events: Networking Events Program | Advise ADB of any Media tour programs or media tours being planned, if any | 2019-11-01 | -
2 | 2.28 | Events: Networking Events Program | Advise ADB of any Tours Program, and post information on website | 2019-11-01 | -
2 | 2.38 | Events: Opening Session Arrangements | Confirm proposed seating plan. Inform that media will be given a designated seating area and a platform for photographers and broadcast media | 2019-11-01 | -
2 | 2.46 | Events: Pre- and Post-Meeting Tours | Post brochure or information on tours and registration requirements on host country website | 2019-11-01 | -
3 | 3.9 | Meetings and ADB Missions | Host country to visit ADB | 2019-11-01 | -
3 | 3.1 | Meetings and ADB Missions | Arrange and host ADB President's visit to host city | 2019-11-01 | -
6 | 6.8 | Hotel Accommodation | Post information about hotel bookings on host country website | 2019-11-01 | -
7 | 7.9 | Space Requirements: Site Inspections & Space Allocations | Agree with ADB on final space allocation and layouts | 2019-11-01 | -
8 | 8.3 | Protocol | Plan for Protocol Mission and propose subject discussion points | 2019-11-01 | -
8 | 8.4 | Protocol | Discuss Airport arrangements and courtesies, ground transport, courtesy calls, seating arrangements at key events and receptions | 2019-11-01 | -
9 | 9.6 | Visas | Post information on visa applications on host country website | 2019-11-01 | -
9 | 9.7 | Visas | Provide a focal point for visa inquiries and facilitation | 2019-11-01 | -
9 | 9.12 | Visa: Tax and Customs Duty Exemption | Issue any documentation required for hotels, shipping agent, etc | 2019-11-01 | -
11 | 11.2 | Information & Conference Technology | Link formatted version on ADB website with relevant host country websites | 2019-11-01 | -
13 | 13.4 | Accreditation and Invitations | Draft invitation copy and eDM (Electronic direct mail) design/template and provide example to ADB | 2019-11-01 | -
17 | 17.3 | Registration | Provide comments on draft sample badges | 2019-11-01 | -
17 | 17.4 | Registration | Agree with ADB on the use of forwarding facility to promote host country events (frequency of broadcast e-mails) | 2019-11-01 | -
19 | 19.3 | Meeting Setups | Agree with ADB on final space allocation and layouts | 2019-11-01 | -
21 | 21.6 | Catering and Refreshments | HC to start completing a Master Catering schedule which includes all the catering requirements across all areas to share with ADB and Caterers/Venues. | 2019-11-01
22 | 22.9 | Staff Support: Locally Engaged Staff | Advise ADB on source and recruitment of host country local staff | 2019-11-01 | -
25 | 25.5 | Sustainability Considerations | Attend training at ADB HQ on sustainable events | 2019-11-01 | -
25 | 25.6 | Sustainability Considerations | Confirm sustainability risk assessment for the Annual Meeting | 2019-11-01 | -
28 | 28.3 | Shipment | Inform ADB of appointed broker to handle shipments | 2019-11-01 | -
11 | 11.5 | Information & Conference Technology | Start planning for the Technical Mission held in January or February | Nov-2019 to Dec-2019 | -
2 | 2.1 | Events: Business Session | Confirm the Chair's availability to chair the Business Session (as per the co-chairing schedule proposed to the Organizing Committee) | 2019-12-01 | -
2 | 2.11 | Events: Business Session | Determine date, time, and venue of ADB President's courtesy call on the Chair | 2019-12-01 | -
2 | 2.12 | Events: Business Session | Confirm the schedule for the briefing of the Chair and Vice-Chairs by the Secretary | 2019-12-01 | -
2 | 2.13 | Events: Business Session | Confirm if the Chair will deliver a combined statement (opening and country statements) or separate statements | 2019-12-01 | -
15 | 15.4 | Security | Provide plan of security perimeter, access and drop-off points, and traffic flow | 2019-12-01 | -
15 | 15.5 | Security | Prepare security guard schedule for all areas of the AM venues | 2019-12-01
15 | 15.6 | Security | Determine security measures and access for service vehicles, deliveries | 2019-12-01 | -
16 | 16.3 | Transport and Traffic Flow | Determine how to allow access for (i) registration, and (ii) delivery of publications | 2019-12-01 | -
16 | 16.4 | Transport and Traffic Flow | Determine parking areas for all vehicles including participants | 2019-12-01
20 | 20.1 | Media and Communications | Provide list of journalists based in the host country, including their email addresses, for the online invitation | 2019-12-01 | -
21 | 21.7 | Catering and Refreshments | Caterers to send menu selection to ADB for transmittal to event organizers | 2019-12-01 | -
24 | 24.3 | Procurement | Host country / ADB to finalize selection of their respective suppliers | 2019-12-01 | -
25 | 25.7 | Sustainability Considerations | Set sustainability objectives and indicators; discuss these with supply chain | 2019-12-01 | -
2 | 2.47 | Events: Pre- and Post-Meeting Tours | Organize registration, payment, if any, and implementation of tours | Dec-2019 to May-2020 | -
2 | 2.39 | Events: Opening Session Arrangements | Advise ADB of Guest of Honor | 2020-01-01 | -
2 | 2.4 | Events: Opening Session Arrangements | Provide list of members of diplomatic corps and local VIPs to be invited | 2020-01-01 | -
2 | 2.41 | Events: Opening Session Arrangements | Advise ADB on webcasting of opening session | 2020-01-01 | -
2 | 2.49 | Events: Sponsored Seminar Program | Sponsors coordinate directly with selected vendors on requirements | 2020-01-01 | -
7 | 7.1 | Space Requirements: Site Inspections & Space Allocations | Submit final floor plans for reproduction | 2020-01-01 | -
9 | 9.8 | Visas | Relay ADB's request to issue appropriate visas to participants to the host country's diplomatic or visa-issuing missions | 2020-01-01 | -
11 | 11.21 | Information & Conference Technology | Submit mobile app to ADB for comments | 2020-01-01 | -
12 | 12.1 | Sponsorship, Partnership and Gifts | Identify what gifts/souvenirs are required across all areas of the Annual Meeting. VIP’s vs Participants | 2020-01-01 | -
12 | 12.11 | Sponsorship, Partnership and Gifts | Advise ADB on any souvenir items to be given to participants | 2020-01-01 | -
16 | 16.5 | Transport and Traffic Flow | Share Transport, parking and Traffic flow plan with all parties | 2020-01-01
19 | 19.4 | Meeting Setups | Submit final floor plans for reproduction | 2020-01-01 | -
20 | 20.11 | Media and Communications | Assist local media to register online | 2020-01-01 | -
24 | 24.4 | Procurement | ADB and host country to send detailed information to suppliers | 2020-01-01 | -
25 | 25.8 | Sustainability Considerations | Propose specific sustainable event activities for environmental, economic and social impacts at the Annual Meeting | 2020-01-01 | -
26 | 26.6 | Printing Reqirements for the Board of Directors | Provide comments on information bulletins (airport reception, liaison officers, airport arrangements, transport, communications and equipment, international telephone calls, return shipment, and badges) | 2020-01-01 | -
26 | 26.8 | Printing: InfoMap and Digital Program of Events | Provide input on InfoMap and digital Program of Events | 2020-01-01 | -
28 | 28.4 | Shipment | Submit necessary documents for tax exemption to shipping company | 2020-01-01 | -
20 | 20.3 | Host Country Media Outreach Program | Implement press related program in consultation with ADB | Jan-2020 to Apr-2020 | -
2 | 2.42 | Events: Opening Session Arrangements | Discuss opening session scenario; provide feedback to ADB | Jan-2020 to May-2020 | -
6 | 6.9 | Hotel Accommodation | Process hotel reservations, cancellations | Jan-2020 to May-2020 | -
6 | 6.1 | Hotel Accommodation | Provide reports on hotel bookings to ADB as required | Jan-2020 to May-2020 | -
25 | 25.9 | Sustainability Considerations | Coordinate with venue(s) and suppliers to monitor and measure sustainability results | Jan-2020 to May-2020 | -
2 | 2.5 | Events: ADB Seminars | Confirm logistical arrangements for all seminars with ADB | 2020-02-01 | -
2 | 2.6 | Events: ADB Seminars | Discuss content and arrangements for live streaming of key official events as well as ADB videos and promotional materials of sponsors/partners on LCD screens | 2020-02-01 | -
2 | 2.14 | Events: Business Session | Discuss and confirm logistical arrangements for the business session (including a dry run before the business session) | 2020-02-01 | -
2 | 2.16 | Events: Governors’ Plenary | Confirm logistical arrangements (including dry run) | 2020-02-01 | -
2 | 2.2 | Events: Host Country Events | Provide ADB with an executive summary of the program | 2020-02-01 | -
2 | 2.29 | Events: Networking Events Program | Provide list of names of host country special invitees (i.e., local VIPs) | 2020-02-01 | -
2 | 2.3 | Events: Networking Events Program | Provide list of names of incumbent members of diplomatic corps of ADB members in host country | 2020-02-01 | -
2 | 2.31 | Events: Networking Events Program | Provide detailed protocol scenarios and information on transport for VIPs at host country networking events | 2020-02-01 | -
3 | 3.11 | Meetings and ADB Missions | Arrange and host ADB technical mission to host city | 2020-02-01 | -
5 | 5.5 | Branding the Annual Meeting | Technical mission to the venue and meeting of relevant suppliers | 2020-02-01 | -
8 | 8.5 | Protocol | If the Guest of Honor is the head of state or government of Host Country, arrange for ADB protocol team to meet their counterparts | 2020-02-01 | -
11 | 11.6 | Information & Conference Technology | Test wiring and equipment required | 2020-02-01 | -
11 | 11.22 | Information & Conference Technology | Launch mobile app | 2020-02-01 | -
12 | 12.7 | Sponsorship, Partnership and Gifts | Agree on location of sponsors'/partners’ areas, signs | 2020-02-01 | -
14 | 14.5 | Airport Reception | Provide draft airport reception plan | 2020-02-01 | -
14 | 14.6 | Airport Reception | Finalize VIP and other participants' reception procedures | 2020-02-01 | -
14 | 14.7 | Airport Reception | Provide airport floor plans (for inclusion in arrangements paper) | 2020-02-01 | -
14 | 14.8 | Airport Reception | Prepare staffing plan to share with the International Airport management team | 2020-02-01 | -
15 | 15.7 | Security | Present security plan, including emergency evacuation, to ADB head of security | 2020-02-01 | -
15 | 15.8 | Security | Discuss detailed security scenarios with ADB Security Coordinator | 2020-02-01 | -
16 | 16.6 | Transport and Traffic Flow | Review arrangements for assigned cars and shuttle bus schedules | 2020-02-01 | -
16 | 16.7 | Transport and Traffic Flow | Review arrangements for traffic flow at meeting venue and networking events venues | 2020-02-01 | -
16 | 16.8 | Transport and Traffic Flow | Review transport advisory for participants | 2020-02-01 | -
16 | 16.9 | Transport and Traffic Flow | Finalize parking, vehicle movement signage requirements for all areas of AM | 2020-02-01
17 | 17.5 | Registration | Determine access procedure for nonregistered meeting invitees, if any | 2020-02-01 | -
17 | 17.6 | Registration | Assign focal person to coordinate registration of members of Host Country Secretariat for their registration | 2020-02-01 | -
17 | 17.7 | Registration | Determine how to register, provide access to local staff, and inform ADB | 2020-02-01 | -
17 | 17.8 | Registration | Assign focal person to register host country dignitaries and special invitees | 2020-02-01 | -
17 | 17.9 | Registration | Provide facilities and technical personnel to test and support ADB registration equipment | 2020-02-01 | -
17 | 17.1 | Registration | Agree on and establish accreditation and registration procedures onsite | 2020-02-01 | -
18 | 18.3 | Meeting Services | HC/PCO to allocate a suitable space for each meeting service requirements and add to scaled floorplans and Utilization table | 2020-02-01 | -
22 | 22.1 | Staff Support: Briefings | Confirm date of hiring, training and briefing of locally engaged staff | 2020-02-01 | -
23 | 23.7 | Furniture and Supplies | Ensure that the audio, video and other equipment and furniture provided are of appropriate ADB standards | 2020-02-01 | -
24 | 24.5 | Procurement | ADB and host country to meet with suppliers to discuss issues, details, test and select items as necessary | 2020-02-01 | -
26 | 26.9 | Printing: InfoMap and Digital Program of Events | Provide telephone and cell phone numbers for directory | 2020-02-01 | -
26 | 26.1 | Printing: InfoMap and Digital Program of Events | Review final InfoMap and digital Program of Events | 2020-02-01 | -
9 | 9.9 | Visas | Process visas of Annual Meeting participants, including international media, as quickly as possible | Feb-2020 to Apr-2020 | -
2 | 2.17 | Events: Governors’ Plenary | Decide who will moderate the plenary (confirm Chair's availability if decided upon) | 2020-03-01 | -
5 | 5.6 | Branding the Annual Meeting | Begin production of event materials | 2020-03-01 | -
7 | 7.11 | Space Requirements: Site Inspections & Space Allocations | Agree on turnaround time for meeting and seminar rooms | 2020-03-01 | -
7 | 7.12 | Space Requirements: Site Inspections & Space Allocations | Agree on exact set-up and dismantling dates | 2020-03-01 | -
7 | 7.13 | Space Requirements: Site Inspections & Space Allocations | Appoint room managers to oversee each venue where meetings and events will take place | 2020-03-01 | -
12 | 12.8 | Sponsorship, Partnership and Gifts | Finalize all sponsorship/partnership matters in consultation with ADB | 2020-03-01 | -
12 | 12.9 | Sponsorship, Partnership and Gifts | Provide ADB with complete list of sponsors/partners and their promotion activities | 2020-03-01 | -
16 | 16.1 | Transport and Traffic Flow | Determine schedule and itineraries of shuttle buses | 2020-03-01 | -
18 | 18.4 | Meeting Services | HC to allocate staff to each Meeting Service. Ensure these staff are properly briefed at each location | 2020-03-01 | -
18 | 18.5 | Meeting Services | Ensure all meeting services are finalised with ADB. Staffing, meeting service location and signage is agreed/approved | 2020-03-01 | -
19 | 19.5 | Meeting Setups | Agree on turnaround time for meeting and seminar rooms | 2020-03-01 | -
19 | 19.6 | Meeting Setups | Agree on exact set-up and dismantling dates | 2020-03-01 | -
19 | 19.7 | Meeting Setups | Ensure all equipment, furniture and setup requirements is ordered for each meeting and event | 2020-03-01 | -
19 | 19.8 | Meeting Setups | Appoint room managers to oversee each venue where meetings and events will take place | 2020-03-01 | -
21 | 21.8 | Catering and Refreshments | Caterers to confirm with ADB that requirements will be met and of high standard | 2020-03-01 | -
22 | 22.1 | Staff Support: Locally Engaged Staff | If considered necessary, send a representative for the panel interviews of ADB local staff | 2020-03-01 | -
26 | 26.7 | Printing Reqirements for the Board of Directors | Provide comments on official events paper | 2020-03-01 | -
27 | 27.4 | Payments by ADB | Suppliers send contract or agreement to ADB; negotiation commences | 2020-03-01 | -
28 | 28.5 | Shipment | Handle customs clearance and actual shipment from ADB | Mar-2020 to Apr-2020 | -
2 | 2.32 | Events: Networking Events Program | Prepare invitations to host country events, where relevant, and send by email | 2020-04-01 | -
2 | 2.43 | Events: Opening Session Arrangements | Finalize arrangements for opening session in consultation with ADB | 2020-04-01 | -
7 | 7.4 | Space Requirements: Offices | Provide offices to advance team (i.e., Secretariat team, Registration team and Media team) | 2020-04-01 | -
11 | 11.7 | Information & Conference Technology | Provide all wiring, equipment needed and webcasting to meet the requirements set out in the eGreen-book | 2020-04-01 | -
11 | 11.8 | Information & Conference Technology | Install all LCD screens and seminar equipment (2 days before use) | 2020-04-01 | -
11 | 11.1 | Information & Conference Technology | Provide telephones that can call internally, boss-to-secretary, and externally (within the city) as well as some international direct dial lines | 2020-04-01 | -
11 | 11.12 | Information & Conference Technology | Share onsite communication plan (Communication Routing) to ADB and HC teams (refer to sample communication plan) | 2020-04-01 | -
13 | 13.5 | Accreditation and Invitations | Provide names and e-mail addresses of contact persons for host country guests, including local dignitaries, members of the diplomatic corps and members of host country secretariat, who will forward the ADB invitation to invited host country guests | 2020-04-01 | -
14 | 14.9 | Airport Reception | Train all staff and volunteers | 2020-04-01 | -
14 | 14.1 | Airport Reception | Conduct a dry run of reception procedures with the ADB advance party | 2020-04-01 | -
15 | 15.9 | Security | Provide telephone numbers for emergency information | 2020-04-01 | -
15 | 15.1 | Security | Design color-coded badges for local staff and police access to restricted areas such as the Governors' Lounge | 2020-04-01 | -
16 | 16.11 | Transport and Traffic Flow | Finalize shuttle bus schedule booklet, if any, in consultation with ADB | 2020-04-01 | -
16 | 16.13 | Transport and Traffic Flow | Conduct dry run for shuttles with ADB advance team | 2020-04-01 | -
17 | 17.11 | Registration | If applicable, provide a prototype of locally engaged staff badges to security, police, and ADB | 2020-04-01 | -
17 | 17.12 | Registration | Provide download instructions for the ADB App and provide a user guide to registration staff as part of the training. | 2020-04-01 | -
22 | 22.2 | Staff Support: Briefings | Set up appointment, venue, and equipment required for briefing by ADB | 2020-04-01 | -
22 | 22.12 | Staff Support: Locally Engaged Staff | Arrange briefings for local staff by host country and ADB Secretariat | 2020-04-01 | -
22 | 22.15 | Staff Support: Liaison Officers | Arrange briefing for liaison officers to be conducted with ADB | 2020-04-01 | -
22 | 22.16 | Staff Support: Liaison Officers | Agree with ADB on assignment of liaison officers for key officials, including ADB President and spouse or partner | 2020-04-01 | -
22 | 22.17 | Staff Support: Liaison Officers | Give ADB list of liaison officers and their cell phone numbers | 2020-04-01 | -
24 | 24.6 | Procurement | Host country / ADB to finalize arrangements for suppliers and providers | 2020-04-01 | -
26 | 26.13 | Printing | Print materials | 2020-04-01 | -
28 | 28.6 | Shipment | Provide storage as necessary for ADB shipments | 2020-04-01 | -
5 | 5.7 | Branding the Annual Meeting | Installation of event materials | Apr-2020 to May-2020 | -
9 | 9.13 | Visa: Tax and Customs Duty Exemption | Ensure hotels and other relevant entities implement tax exemption procedures | Apr-2020 to May-2020 | -
11 | 11.11 | Information & Conference Technology | Provide cell phones for ADB personnel for making local calls | Apr-2020 to May-2020 | -
16 | 16.12 | Transport and Traffic Flow | Train all drivers on routes to and from all meeting venues | Apr-2020 to May-2020 | -
21 | 21.9 | Catering and Refreshments | Caterer to deliver goods and services and submit bill for payment | Apr-2020 to May-2020 | -
22 | 22.11 | Staff Support: Locally Engaged Staff | Train local staff in their jobs, including drivers of shuttle buses and liaison officers | Apr-2020 to May-2020 | -
25 | 25.1 | Sustainability Considerations | Communicate sustainability activities to HOC, local community and other stakeholders | Apr-2020 to May-2020 | -
1 | 1.5 | Budget | Ensure all payments are settled and send pending bills to ADB | 2020-05-01 | -
2 | 2.7 | Events: ADB Seminars | Provide logistical requirements and local staff required for seminar series | 2020-05-01 | -
2 | 2.21 | Events: Host Country Events | Provide ADB with a synopsis of the program for inclusion in the post-Annual Meeting publication, Highlights | 2020-05-01 | -
2 | 2.33 | Events: Networking Events Program | Implement Tours Program (if any) | 2020-05-01 | -
2 | 2.44 | Events: Opening Session Arrangements | Implement opening session protocol scenario | 2020-05-01 | -
3 | 3.12 | Meetings and ADB Missions | Provide feedback to ADB on experience hosting Annual Meeting. PCO or HC to organise a Debrief meeting with all stakeholders involved | 2020-05-01 | -
3 | 3.13 | Meetings and ADB Missions | PCO or HC to provide a final post event report | 2020-05-01 | -
7 | 7.5 | Space Requirements: Offices | Ensure ADB offices are furnished and equipped in accordance with ADB requirements | 2020-05-01 | -
7 | 7.6 | Space Requirements: Offices | Open all other ADB offices | 2020-05-01 | -
7 | 7.14 | Space Requirements: Site Inspections & Space Allocations | Ensure that all meeting spaces are set up in accordance with requirements one hour before the meeting or event for checking | 2020-05-01 | -
13 | 13.6 | Accreditation and Invitations | Provide final list of invitees for the host country luncheon to ADB at least 5 days before the event | 2020-05-01 | -
13 | 13.7 | Accreditation and Invitations | Send invitations (by email) for host country luncheon and host country reception to invitees in advance | 2020-05-01 | -
14 | 14.11 | Airport Reception | Set up reception desk, separate immigration lane, shuttle bus stop, and signs | 2020-05-01 | -
15 | 15.11 | Security | Meet with ADB Security Advisory Committee every day during Annual Meeting | 2020-05-01 | -
17 | 17.13 | Registration | During the Annual Meeting, post ADB staff at the registration center to accredit onsite registrants | 2020-05-01 | -
19 | 19.9 | Meeting Setups | Ensure that all meeting spaces are set up in accordance with requirements one hour before the meeting or event for checking | 2020-05-01 | -
22 | 22.3 | Staff Support: Briefings | Appoint locally engaged staff protocol and onsite briefing | 2020-05-01 | -
22 | 22.18 | Staff Support: Liaison Officers | Set up meetings between liaison officers and their VIPs | 2020-05-01 | -
24 | 24.7 | Procurement | Host country / ADB to check that all services and products are provided as required | 2020-05-01 | -
25 | 25.11 | Sustainability Considerations | Provide previously-agreed, relevant data to measure implementation of sustainability objectives | 2020-05-01 | -
28 | 28.7 | Shipment | Handle return shipments including packing, storage, and transport to port of exit | 2020-05-01 | -
27 | 27.6 | Payments by ADB | For payments to be made after the Annual Meeting, ADB reviews the advance copy of bill using the catering and refreshments schedule or accommodation booking advice as a basis. | 2020-05-05 | -
27 | 27.8 | Payments by ADB | ADB brings original invoice or bill and supporting documents to ADB headquarters for processing. | 2020-05-05 | -
27 | 27.7 | Payments by ADB | Supplier prepares final bill in the agreed currency | 2020-05-06 | -
27 | 27.9 | Payments by ADB | Processing of payment takes 2–3 weeks, assuming all documents are complete and the supplier information form is already set up. | Mid-May to July 2020 | -
1 | 1.6 | Budget | Provide breakdown of costs incurred by host country and sponsors | 2020-06-01 | -
27 | 27.1 | Payments by ADB | Payment is through wire transfer and may take a maximum of 15 days after the value date for ADB’s bank to remit payment to the bank of the supplier. | June to July 2020 | -
27 | 27.3 | Payments by ADB | ADB confirms the online registration. | after completing all the documentary requirements | -
27 | 27.5 | Payments by ADB | Advance payment process | After confirmation of online supplier registration | -