## PROJECT GANTT 12mth
Technical Procurement & Onsite Gantt Chart | [30 empty] | Updated : |  |  |  | 26th Aug 2014
Year |  | Start Month | [28 empty] | LEGEND
2014 |  | 8 | [27 empty] | 1 |  |  | HOST Submission of RFP
Start Day | [29 empty] | 2 |  |  | Submission of Bids
1 | 1: Sunday, 2: Monday | [28 empty] | 3 |  |  | Awarding Period
[30 empty] | 4 |  |  | ADB Submission of Docs
>>Enter Year, Start Day, Start Month in Yellow Cells above | [29 empty] | 5 |  |  | ADB/HOST Pre_Pro
>>> Enter Detail in cream cells below and shade dates accordingly | [29 empty] | 6 |  |  | ADB Mission
[30 empty] | 7 |  |  | HOST Review of Bids
[30 empty] | 8 |  |  | Installation/Load In
[30 empty] | 9 |  |  | Commissioning Days
[30 empty] | 10 |  |  | ADB Annual Meeting
2014-2015 |  |  |  |  | TECHNICAL - MILESTONE PLANNING
[42]
| Responsible | Start | Finish | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | NOTES: (non Printing)
2014-08-01 | [8 empty] | 2014-08-01 | 2014-08-02 | 2014-08-03 | 2014-08-04 | 2014-08-05 | 2014-08-06 | 2014-08-07 | 2014-08-08 | 2014-08-09 | 2014-08-10 | 2014-08-11 | 2014-08-12 | 2014-08-13 | 2014-08-14 | 2014-08-15 | 2014-08-16 | 2014-08-17 | 2014-08-18 | 2014-08-19 | 2014-08-20 | 2014-08-21 | 2014-08-22 | 2014-08-23 | 2014-08-24 | 2014-08-25 | 2014-08-26 | 2014-08-27 | 2014-08-28 | 2014-08-29 | 2014-08-30 | 2014-08-31
Vendor Procurement & Pre Production |  | 2014-08-01 | 2015-04-01
2014-09-01 |  |  |  |  | 2014-09-01 | 2014-09-02 | 2014-09-03 | 2014-09-04 | 2014-09-05 | 2014-09-06 | 2014-09-07 | 2014-09-08 | 2014-09-09 | 2014-09-10 | 2014-09-11 | 2014-09-12 | 2014-09-13 | 2014-09-14 | 2014-09-15 | 2014-09-16 | 2014-09-17 | 2014-09-18 | 2014-09-19 | 2014-09-20 | 2014-09-21 | 2014-09-22 | 2014-09-23 | 2014-09-24 | 2014-09-25 | 2014-09-26 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30
Issue Technical Rider to Host | ADB | 2014-09-05 | 2014-09-09 | bar: 2014-09-05 to 2014-09-09
Site Visit #1 - Mission | ADB/HOST | 2014-09-11 | 2014-09-17 | bar: 2014-09-11 to 2014-09-17
Review Rider with Host | ADB/HOST | 2014-09-14 | 2014-10-14 | bar: 2014-09-14 to 2014-09-30
2014-10-01 | [6 empty] | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-10-10 | 2014-10-11 | 2014-10-12 | 2014-10-13 | 2014-10-14 | 2014-10-15 | 2014-10-16 | 2014-10-17 | 2014-10-18 | 2014-10-19 | 2014-10-20 | 2014-10-21 | 2014-10-22 | 2014-10-23 | 2014-10-24 | 2014-10-25 | 2014-10-26 | 2014-10-27 | 2014-10-28 | 2014-10-29 | 2014-10-30 | 2014-10-31
Review Rider with Host | ADB | 2014-09-14 | 2014-10-14 | bar: 2014-10-01 to 2014-10-14
2014-11-01 | [9 empty] | 2014-11-01 | 2014-11-02 | 2014-11-03 | 2014-11-04 | 2014-11-05 | 2014-11-06 | 2014-11-07 | 2014-11-08 | 2014-11-09 | 2014-11-10 | 2014-11-11 | 2014-11-12 | 2014-11-13 | 2014-11-14 | 2014-11-15 | 2014-11-16 | 2014-11-17 | 2014-11-18 | 2014-11-19 | 2014-11-20 | 2014-11-21 | 2014-11-22 | 2014-11-23 | 2014-11-24 | 2014-11-25 | 2014-11-26 | 2014-11-27 | 2014-11-28 | 2014-11-29 | 2014-11-30
Submit RFPs & Onsite Briefing | HOST | 2014-11-01 | 2014-11-14 | bar: 2014-11-01 to 2014-11-14
Vendor Comms & Queries | HOST/ADB | 2014-11-14 | 2014-11-28 | bar: 2014-11-14 to 2014-11-28
2014-12-01 |  |  |  |  | 2014-12-01 | 2014-12-02 | 2014-12-03 | 2014-12-04 | 2014-12-05 | 2014-12-06 | 2014-12-07 | 2014-12-08 | 2014-12-09 | 2014-12-10 | 2014-12-11 | 2014-12-12 | 2014-12-13 | 2014-12-14 | 2014-12-15 | 2014-12-16 | 2014-12-17 | 2014-12-18 | 2014-12-19 | 2014-12-20 | 2014-12-21 | 2014-12-22 | 2014-12-23 | 2014-12-24 | 2014-12-25 | 2014-12-26 | 2014-12-27 | 2014-12-28 | 2014-12-29 | 2014-12-30 | 2014-12-31
Submission of Vendor Bids | HOST | 2014-12-01 | 2014-12-07 | bar: 2014-12-01 to 2014-12-07
Review Completed RFP | HOST | 2014-12-07 | 2014-12-28 | bar: 2014-12-07 to 2014-12-28
2015-01-01 | [7 empty] | 2015-01-01 | 2015-01-02 | 2015-01-03 | 2015-01-04 | 2015-01-05 | 2015-01-06 | 2015-01-07 | 2015-01-08 | 2015-01-09 | 2015-01-10 | 2015-01-11 | 2015-01-12 | 2015-01-13 | 2015-01-14 | 2015-01-15 | 2015-01-16 | 2015-01-17 | 2015-01-18 | 2015-01-19 | 2015-01-20 | 2015-01-21 | 2015-01-22 | 2015-01-23 | 2015-01-24 | 2015-01-25 | 2015-01-26 | 2015-01-27 | 2015-01-28 | 2015-01-29 | 2015-01-30 | 2015-01-31
Award Vendors | HOST | 2015-01-03 | 2015-02-15
2015-02-01 |  |  |  | 2015-02-01 | 2015-02-02 | 2015-02-03 | 2015-02-04 | 2015-02-05 | 2015-02-06 | 2015-02-07 | 2015-02-08 | 2015-02-09 | 2015-02-10 | 2015-02-11 | 2015-02-12 | 2015-02-13 | 2015-02-14 | 2015-02-15 | 2015-02-16 | 2015-02-17 | 2015-02-18 | 2015-02-19 | 2015-02-20 | 2015-02-21 | 2015-02-22 | 2015-02-23 | 2015-02-24 | 2015-02-25 | 2015-02-26 | 2015-02-27 | 2015-02-28
Award Vendors | HOST | 2015-01-03 | 2015-02-15 | bar: 2015-02-01 to 2015-02-15
Review Scope of Works with Vendor | HOST/ADB | 2015-02-01 | 2015-03-15
2015-03-01 |  |  |  | 2015-03-01 | 2015-03-02 | 2015-03-03 | 2015-03-04 | 2015-03-05 | 2015-03-06 | 2015-03-07 | 2015-03-08 | 2015-03-09 | 2015-03-10 | 2015-03-11 | 2015-03-12 | 2015-03-13 | 2015-03-14 | 2015-03-15 | 2015-03-16 | 2015-03-17 | 2015-03-18 | 2015-03-19 | 2015-03-20 | 2015-03-21 | 2015-03-22 | 2015-03-23 | 2015-03-24 | 2015-03-25 | 2015-03-26 | 2015-03-27 | 2015-03-28 | 2015-03-29 | 2015-03-30 | 2015-03-31
Review Scope of Works with Vendor | HOST/ADB | 2015-02-01 | 2015-03-15 | bar: 2015-03-01 to 2015-03-15
Site Visit #2 - Technical Mission | ADB/HOST | 2015-03-11 | 2015-03-17 | bar: 2015-03-11 to 2015-03-17
Finalise all Vendor supplies | HOST/ADB | 2015-03-15 | 2015-04-10 | bar: 2015-03-15 to 2015-03-31
2015-04-01 | [6 empty] | 2015-04-01 | 2015-04-02 | 2015-04-03 | 2015-04-04 | 2015-04-05 | 2015-04-06 | 2015-04-07 | 2015-04-08 | 2015-04-09 | 2015-04-10 | 2015-04-11 | 2015-04-12 | 2015-04-13 | 2015-04-14 | 2015-04-15 | 2015-04-16 | 2015-04-17 | 2015-04-18 | 2015-04-19 | 2015-04-20 | 2015-04-21 | 2015-04-22 | 2015-04-23 | 2015-04-24 | 2015-04-25 | 2015-04-26 | 2015-04-27 | 2015-04-28 | 2015-04-29 | 2015-04-30
Finalise all Vendor supplies | HOST/ADB | 2015-03-15 | 2015-04-10 | bar: 2015-04-01 to 2015-04-10
Vendor Venue Access & Installation (Suggested) | HOST/ADB | 2015-03-23 | 2015-03-28 | bar: 2015-04-23 to 2015-04-28
Commissioning Days (Suggested min 48hrs) | HOST/ADB | 2015-03-29 | 2015-03-30 | bar: 2015-04-29 to 2015-04-30
ADB Technical Consulting Team Onsite (FuzionFactory) | ADB | 2015-04-22 | 2015-05-06 | bar: 2015-04-22 to 2015-04-30
2015-05-01 | [8 empty] | 2015-05-01 | 2015-05-02 | 2015-05-03 | 2015-05-04 | 2015-05-05 | 2015-05-06 | 2015-05-07 | 2015-05-08 | 2015-05-09 | 2015-05-10 | 2015-05-11 | 2015-05-12 | 2015-05-13 | 2015-05-14 | 2015-05-15 | 2015-05-16 | 2015-05-17 | 2015-05-18 | 2015-05-19 | 2015-05-20 | 2015-05-21 | 2015-05-22 | 2015-05-23 | 2015-05-24 | 2015-05-25 | 2015-05-26 | 2015-05-27 | 2015-05-28 | 2015-05-29 | 2015-05-30 | 2015-05-31
Prep Day | HOST/ADB | 2015-05-01 | 2015-05-01 | bar: 2015-05-01
Conference Days (Annual Meeting) | HOST/ADB | 2015-05-02 | 2015-05-05 | bar: 2015-05-02 to 2015-05-05
ADB Technical Consulting Team Onsite (FuzionFactory) | ADB | 2015-04-22 | 2015-05-06 | bar: 2015-05-01 to 2015-05-06
2015-06-01 |  |  |  |  | 2015-06-01 | 2015-06-02 | 2015-06-03 | 2015-06-04 | 2015-06-05 | 2015-06-06 | 2015-06-07 | 2015-06-08 | 2015-06-09 | 2015-06-10 | 2015-06-11 | 2015-06-12 | 2015-06-13 | 2015-06-14 | 2015-06-15 | 2015-06-16 | 2015-06-17 | 2015-06-18 | 2015-06-19 | 2015-06-20 | 2015-06-21 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-27 | 2015-06-28 | 2015-06-29 | 2015-06-30
2015-07-01 | [6 empty] | 2015-07-01 | 2015-07-02 | 2015-07-03 | 2015-07-04 | 2015-07-05 | 2015-07-06 | 2015-07-07 | 2015-07-08 | 2015-07-09 | 2015-07-10 | 2015-07-11 | 2015-07-12 | 2015-07-13 | 2015-07-14 | 2015-07-15 | 2015-07-16 | 2015-07-17 | 2015-07-18 | 2015-07-19 | 2015-07-20 | 2015-07-21 | 2015-07-22 | 2015-07-23 | 2015-07-24 | 2015-07-25 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-29 | 2015-07-30 | 2015-07-31