## MATRIX
CREATIVE MATRIX TEMPLATE_ONSITE ARTWORK
ARTWORK DONE | ARTWORK DESPATCHED | ITEM | LOCATION | VENUE | IMAGE / LOCATION REFERENCE | QUANTITY | DESIGN / ARTWORK REFERENCE | DESCRIPTION | SPECIFICATIONS | CONTENT / COPY / LOGO | FABRICATION / SUBSTRATE | DESIGNED BY | PRODUCTION DEADLINE | CLIENT REVIEW | AMENDS | NOTES | APPROVED | INSTALLATION DATE | INSTALLATION NOTES | DONE
MISCELLANEOUS
|  | Directional personell hand held sign | Denarau | Denarau Road |  | 10 |  |  | 300h x 700 w Quantity: 5 | Artwork Kind 1: Delegate Parking Directional arrow pointing left | [5 empty] | To be sent to XXX for approval |  | 30th April | ABC Printery Deliver to: Attention to: XXX to install
|  |  | Roadside directing to Car Parks | Denarau |  | 15 |  | Small single sided sign on spike to direct delegates on Denarau Road to delegate parking | 400mm h x 500mm w Quantity: 20 | Generic P sign with arrows for each major intersection in Denarau. Arrows to be printed as PVC vinyl sticker and placed according to direction required *arrow placed onto sign onsite Artwork Kind 1: Delegate Parking x 10 Artwork Kind 2: VIP Transport Compound x10 (arrow) | [5 empty] | To be sent to XXX for approval |  | 27th April | ABC Printery Deliver to: Attention to: XXX to install
REGISTRATION ZONE
|  | Registration Fascia | Registration Counter | Golf Club |  | 6 |  | Really big bold text to simply show the type of lane. logo at the bottom of desk |  | REGISTRATION Artwork Kind 1: Front Facia Signage Removable signage to be placed above the counter: Sign 1: Media Sign 2: CSO Sign 3: Walk-In Registration Sign 4: Accreditation office | [7 empty] | 25th April | Tony & AAM Team
|  | Registration Fascia | Registration Counter | Golf Club |  | 6 |  | Brand Banner |  | REGISTRATION logos on bottom rego desk | [7 empty] | 25th April | Tony & AAM Team
AIRPORT
VENUE 1
VENUE 2
VENUE 3
|  | VENUE 4 | [7 empty] | vChamps Roundtable
|  | TRANSPORT | [7 empty] | D
|  | VIP ACCOMODATONS | [7 empty] | D

## Branding Deadlines
BRANIDNG DEADLINES
Date TBC
Present initial designs for event branding including: directional signage, venue signage, outside branding, stage set design, marquees and event branding & theming
Date TBC
Feedback from MCS & ADB
Date TBC
1. Agency revert with first set of changes.
2. MCS & ADB to present internally for comment and feedback.
Date TBC
MCS to brief agency on changes to first set of designs.
Date TBC
Agency to present at Stakeholder WIP for comment and feedback.
Date TBC
Misfits to revert with second set of changes.
Date TBC
MCS & ADB to revert with comment and feedback on second set of changes.
Date TBC
Misfits to revert with final changes
Date TBC
MCS & ADB to approve final changes.
Early March 2019
Misfits to start production on all signage.