## Sheet1
TASK | VIP | Other Participants | Complete Y/N | Comments
Create overall airport action plan.
Indicate the ports of entry (i.e., international and domestic airports as well as other ports of entry). | X | X
Outline communication, coordination, and facilitation plan between immigration, customs, airline officials, hotels, and the Annual Meeting transport desk. | X | X
Indicate the details of (a) airport reception service, (b) transport coordination service, and (c) hospitality desk in the arrival and departure halls. | X | X
Provide airport site plan and vicinity map.
Indicate proposed location of airport reception desks, which should be easily visible to arriving participants. | X | X
Indicate location of signs. | X | X
Indicate VIP holding area locations (both arrival and departure). | X | X
Indicate other participants’ holding area locations (both arrival and departure). | X | X
Indicate reception flow for VIPs. | X | X
Indicate reception flow for other participants. | X | X
Indicate traffic flow for VIPs and other participants. | X | X
Locate parking lots for buses and VIP cars. | X | X
Agree on identification procedure for participants | X | X
Arrange reception courtesies by host country officials, including by representatives of the Ministry of Foreign Affairs, airport authorities, national airline representatives, and municipal authorities. | X | X
Identify lounge for VIPs.
Identify where ADB personnel and embassy dignitaries will welcome VIPs. | X
Identify where refreshments will be provided. | X
Identify area for liaison officers, drivers, and accompanying persons. | X
Identify vehicle access for pick-up (e.g., the tarmac for the ADB President) | X
Identify arrival gates. | X | X
Identify branding and signage requirements throughout the arrival and departure areas | X | X
Identify quarantine, if required. |  | X
Identify immigration procedures.
Identify visa procedures (i.e., visas on arrival). | X | X
Identify dedicated number of immigration lines. | X | X
Identify baggage claim procedure.
Outline VIP luggage retrieval system. | X | X
Outline other participants' luggage retrieval system. | X | X
Identify customs procedure. | X | X
Identify holding area for participants to escort them to buses.
Identify where refreshments will be provided. |  | X
Identify where schedule of airport transfers will be posted. |  | X
Supply travel itineraries.
ADB to provide VIPs' itineraries. | X | X
Other participants' itineraries to be provided by the professional congress organizer or the local hotel booking agent. | X | X
Outline coordination plan between the host country, customs, immigration, and airport officials. | X | X
Outline coordination plan between the host country and the ADB Annual Meeting transport unit. | X | X
Airport Staffing.
HC/PCO draft a staffing schedule for Airport arrival and departure | X | X
Share staffing schedule with airport for approval | X | X
Provide full name, phone number and all personal information of the staff member in case Airport Management need to do background checks and provide Airport access badges | X | X
Provide area near or in Arrival area for staff to store personal belongings | X | X
Ensure transport and shuttle service.
Arrange chauffeur-driven cars for VIPs (except for the ADB Vice-Presidents, Dean of the ADB Institute, and Secretary, which will be made available upon their arrival at the hotel where they are booked and not at the airport). | X | X
Arrange convoy vehicles for VIPs, such as embassy cars. | X | X
Arrange shuttle service for other participants. | X | X
Ensure other forms of transport, such as taxis, subway, and public buses. | X | X