## Risk Register
<AM Logo Here> |  | RISK MANAGEMENT PROCESS DRAFT RISK REGISTER
DRAFT RISK REGISTER
Date: <date here>
Thematic Heading | No. | Risk | Risk Owner | Existing Controls | Consequence | Likelihood | Initial Risk Rating | Further Treatments | Proposed | Consequences | Likelihood | Residual Risk Rating | Residual Risk Rating Accepted
[8 empty] | Yes/No | Further Treatments |  |  |  | Yes/No
SECURITY
Politically Motivated Violence (Terrorism) | 1A | Terrorist attack targeting the event itself or its participants | Dept of Defense and National Security. | Host nation security and intelligence framework, counterterrorist and policing capability | Moderate | Rare | Low | Yes | The security planning for this event involves a comprehensive threat assessment process by the host nation who will implement a highly resourced security overlay to secure the meeting and its participants. | Moderate | Rare | Low
| 1B | Terrorist attack targeting another location or persons that may have incidental effect upon the event itself or its participants | Dept of Defense and National Security. | Host nation security and intelligence framework, counterterrorist and policing capability | Moderate | Rare | Low | Yes | The security planning for this event involves a comprehensive threat assessment process by the host nation who will implement a highly resourced security overlay to secure the meeting and its participants. | Moderate | Rare | Low
Civil Disorder (Protests, demonstrations, riots) | 2A | Imported civil disorder threat actors | Police | Host nation policing and intelligence framework and capability | Minor | Rare | Low | Yes | ADB to advise upon any knowledge of an potential threat actor or issue motivated group that might travel to Fiji with the intention of conducting protest activity or other form of disruption. | Minor | Rare | Low
| 2B | Local civil disorder threat actors
Crime | 3A | Fraud (all forms including theft) | Police
| 3B | Crimes against the person | Police
| 3C | Malicious denial of service | Police
| 3D | Insiders threats | Police
Border Security | 4A | Weapons (Requests to import as part of CPP or illegal import scenarios)
| 4B | Drones - interruption to aviation
| 4C | Drones - nuisance
TRANSPORT
| 5A | Inability to source and maintain vehicles and or drivers to meet client needs and expectation
| 5B | Reputational risk linked to impact of ADB AM transport operations upon business as usual
| 5C | Flooding or other weather events impacting transport operations
| 5D | Traffics accidents
| 5E | Blocked routes (other factors)
| 5F | Flow on effect to the availability of drivers and or vehicles by access routes being impacted
ENVIRONMENTAL
| 6A | Flooding
| 6B | Cyclone events
| 6C | Extreme Heat and or humidity
| 6D | Tsunami
| 6E | Earthquakes
HEALTH
| 7A | Influenza and other outbreaks
| 7B | Dengue Fever
| 7C | leptospirosis
| 7D | Food poisoning
| 7E | Incapacity of medical services to scale up (including local Hospital)
| 7F | Sudden onset medical emergency involving participant
| 7G | Pre-existing conditions and disabilities not adequately planned for
| 7H | Lack of Ambulance service capacity
INFRASTRUCTURE
| 8A | Malicious denial of service
| 8B | Fresh water - supply interruption
| 8C | Waste water - supply interruption
| 8D | Gas reticulation - supply interruption
| 8E | Public Transport interruption - (Workforce) unavailability
| 8F | Power - supply interruption
| 8G | Data network (significant failure)
| 8H | Telecommunications (significant failure)
| 8I | Airport disruption
| 8J | Venue unavailability
| 8K | Roads and access routes - congestion, obstacles or impediment
COMMUNICATIONS
| 9A | C3
| 9B | Data network (significant failure)
| 9C | Telecommunications (significant failure)
| 9D | Security (MAAC) Venue Failure
LOGISTICS AND PROCUREMENT
| 10A | Air travel delays or disruption with flow on effects to logistics
| 10B | Import timelines for critical equipment and plant and services
| 10C | Non delivery of locally procured goods and services to site or standard (breach of contract)
| 10D | Venue capacity and flexibility
| 10E | Accommodation - participants and host nation requirements
| 10F | Budget limitations
| 10G | Unforeseen external event which diverts host nation resources away from meeting
| 10H | Visa processes
| 10I | Non compliant border arrivals
| 10J | Potential impact of industrial action upon logistics and procurement
REPUTATION
| 11A | Insider Threats?
| 11B | Critical failure - impact upon reputation - impact upon ADB Brand
| 11C | Critical failure - impact upon reputation - impact upon tourism and or perceptions of HC capacity and capability
| 11D | Health Event (outbreaks)
| 11E | Budget - public perceptions re cost/benefit of the event
| 11F | International media focus upon aspects of policy with potential negative perceptions
| 11G | Reputational risk linked to impact upon business as usual
| 11H | Effectiveness of communications and public relations strategy
| 11I | Significant breach of protocol
Notes:
Red text (rows E - N) is example content only

## Risk Assessment Process
RISK MANAGEMENT PROCESS

## Risk Assessment Matrix
RISK ASSESSMENT MATRIX

## Lilkelihood Scale
LIKELIHOOD SCALE

## Consequence Levels
CONSEQUENCE LEVELS
CONSEQUENCES LEVELS
LIMITED Could be expected to cause limited damage to people, the success of the event or reputation | MINOR Could be expected to cause minor damage to people, the success of the event or reputation | MODERATE Could be expected to cause significant damae to people, the success of the event or reputation | MAJOR Could be expected to cause serious damage to people, the success of the event or reputation | SEVERE Could be expected to cause exceptionally grave damage to people, the success of the event or reputation
CONSEQUENCES AND IMPACTS ON OPERATIONS OR FUNCTIONS
Limited | Minor | Moderate | Major | Severe
Operational capacity Cause limited delays or disruptions to event operations or functions | Operational capacity Cause a loss of, or major degradation of, one or more primary enabling service functions for 2 hours or less | Operational capacity Cause a loss of, or major degradation of, one or more primary enabling service functions for 2 to 4 hour | Operational capacity Cause a loss of, or serious degradation of, one or more primary enabling service functions for 4 to 6 hour | Operational capacity Cause a criticial failure of capability resulting in a prolonged period of outage and/or inability to perform one or more of the events key functions for an extended period
Infrastructure/assets localised damage to event infrastructure or assets | Infrastructure/assets Minor damage to event property, systems or assets | Infrastructure/assets Significant damage to event property, systems or assets | Infrastructure/assets Extensive damage to event property, systems or key assets that affects business continuity | Infrastructure/assets Extensive and widespread damage to event property, systems or key assets that affects business continuity
Reputation Limited short-term impact on reputation and status | Reputation Minor impact on reputation and status with some degradation of engagement/relations with Partners, clients and key stakeholders | Reputation Significant impact on reputation andstatus with degradation of engagement/relations with partners, clients and key stakeholders. Significant community/media criticism and dissatisfaction | Reputation Major impact on reputation and status with serious longer-term degradation of engagement/relations with partners, client and key stakeholders. Serious community/media criticis, and dissatisfaction | Reputation Loss of confidence in Government by partners, clients and key stakeholders. Extreme community/media criticism and dissatisfaction
Finances Limited adverse financial impacts | Finances Minor adverse financial impacts | Finances Moderate adverse financial impacts | Finances Major adverse financial impacts | Finances Extremely adverse financial impacts